## 10 November 2023
IMPLEMENTATION PLAN
SEQ # | TASK | TEAM RESPONSIBLE | REP | START TIME | DURATION in MINUTES (Estimate) | SYS DOWNTIME | DATE | DI | STATUS
1 | Service Account Password Request | Profile Team | Selogilwe Tlhale | 15:00 | 5 | N | 10/11/2023 | TBC | TBC
2 | Wait for running jobs to complete | FML IT Team | Config and Dev | 18:00 | 30 | N/A | 10/11/2023 | N/A | TBC
3 | Snapshot DI(Wintel) | Windows Intel Team | Mukesh Mithbawkar | 18:35 | 15 | N | 10/11/2023 | FML-5488 | TBC
4 | Milesroot Backup (Append) | I&SS Team | Brian | 18:35 | 20 | N | 10/11/2023 | REQ2030147 | TBC
5 | Take DB Backup | MS Sever DBA | Shantanu / Swapnil | 18:35 | 5 | N | 10/11/2023 | FML-5475 | TBC
6 | Apply milesroot (Datasource / Jasper Reports / Query files) | Weblogic | Ramakrishna / Balakrishna | 19:00 | 15 | Y | 10/11/2023 | FML-5474 | TBC
7 | Verify Service Account Password Request | Profile Team | Selogilwe Tlhale | 19:00 | 5 | N | 10/11/2023 | TBC | TBC
8 | Deploy Bulk XMLs | Weblogic | Ramakrishna / Balakrishna | 19:05 | 20 | N | 10/11/2023 | FML-5473 | TBC
9 | Data patches/scripts | DBA | Swapnil / Shantanu | 19:25 | 15 | N | 10/11/2023 | TBC | TBC
10 | Restart app server (after DB scripts) | Weblogic | Ramakrishna / Balakrishna | 19:40 | 5 |  | 10/11/2023 | FML-5474 | TBC
11 | User sanity testing | Business Users | Business Users | 19:45 | 120 | N/A | 10/11/2023 | N/A | TBC

## Rollback Plan
ROLLBACK PLAN
SEQ # | TASK | TEAM RESPONSIBLE | REP | DURATION (Estimate) | DATE | DI | STATUS
1 | Bring down Miles Prod | WebLogic | Ramakrishna / Balakrishna | Unknown | 10/11/2023 | N/A
2 | I&SS Backup Restore | I&SS | Brian | Unknown | 10/11/2023 | REQ2030147
1 | Snapshot DI(Wintel) Restore | Windows Intel | Leyds, Gaylan / Jaravani, Alfred | Unknown | 10/11/2023 | FML-5365
3 | DB Restore | DBA | Shantanu / Swapnil | Unknown | 10/11/2023 | FML-5475
4 | Restart Miles Prod | WebLogic | TBC | Unknown | 10/11/2023 | FML-54743
5 | Apply Rollback XMLs | WebLogic | TBC | Unknown | 28/10/2023