## Regression Testing
| FML-5164 = Web logis | FML-5163 = XMLs | FML-5165 = Database
Ready for Production in September 2023
# | Sofico Jira # | INC # | FML # | DI tickets | QA Regression testing | RT46/ CORP/ BOTH | Description | Issue Description | Resolution | Business User | Comments
1 | WBM3QA-939 | INC6060608/ INC6060767/ INC6057901 | FML-5151 |  |  | RT46 | M3 & Corp - On Accident Pre-inspection does not validate when cost and Recharge amount is captured - GoLive | In Pre-Inspection process, the system needs to validate any recharge and cost amounts when uploading Final Inspection by Call Centre. | When entering in a value on the assesment order, there is a validation that is run, and if a vlue is seen a hard block/error message prompts the agent to remove the rand value. | Zaheer, Vishek, Jadyn
2 | WBM3QA-945 | INC6060633 | FML-5071 |  | Pass | RT46 | M3 - Data Integration - When a merchant is selected, a validation is needed on Draft --> Pre-Authorisation status change to ensure that a supplier that has been allocated has RT46 Agreement = TRUE | When a merchant is selected (whether manual selection or via the WAE), a validation is needed on order status “Pre-Authorisation” status to ensure that specific supplier that has been allocated is RT46 Agreement = TRUE. This validation will be triggered when the status changes from Draft → Pre-Authorisation. | The solution here is validation on all RT46 orders when a merchant has been assigned or selected. The validation checks that the specifc merchant/supplier has the RT46 Agreement ticked (TRUE). If not, the Hard Block error is displayed. | Zaheer, Vishek, Jadyn
3 | WBM3QA-983 | INC6017731 | FML-5036 |  | Pass | RT46 | M3 - Bypass the Required Documents to Activate Supplier - PostGoLive | Business needed a solution to bypass the Required Documents to Activate Supplier (all 9 documents) for manual onboarding of merchants received from FlowCentric post go live. This will reduce the turnaround time for merchant onboarding by merchant department and will help in processing the onboarding. | For the onboarding of RT46 merchnats, the document storage for their onboarding document are still FLowCentric, therefore to alleviate doc storage on Miles, there is a bypass on the comulary documents to be uploaded for new RT46 merchants being loaded. | Chanel, Vishek, Arthi
4 | WBM3QA-1075 | INC6017658 | FML-5040 |  |  | CORP | CORP - Main Repair Order switching to OPL contract when loading accident claims | When navigating from RMT ribbon into Incident/Accident order, the system defaults to the OPL contract instead of MM contract. | @Travis to provide more context please | Travis, Warren
5 | WBM3QA-1109 | INC6060642 | FML-5070 |  | Pass | RT46 | M3 Selections- Merchants Dept - We need to be able to pull reports. | Buness needs to pull a report on all merchants brought into Miles with no RT46 agreement and once off supplier tick. Reports must contain the Auto Card Merchant codes and addresses along with the other detail that already populates. When pulling reports on work orders, to track allocations to merchants between specific date ranges, we are unable to pull this report between specified timelines for example jobs allocated in the past 7 days or month to date/year to date etc. Currently we can only pull a full report not specifying the date however this report is too large to be downloaded/extracted. | The ability to pull reports granted to those specific roles | Chanel, Vishek, Arthi
6 | WBM3QA-1125 | INC5943653 | FML-5038 |  |  | RT46 | M3 Prod - SAPS TO + TRACKING is being sent to supplier instead of a Customer | The TO SAPS + TRACKING document gets sent to the Supplier instead of it being sent to the Customer. | The document mapping for the respective emails addresses have been updated to pull the correct email address. For SAPS, the linked WO will provide the MT users linked to the SAPS Garage. | Zaheer, Vishek, Jadyn
7 | WBM3QA-1131 | INC6001989 | FML-5016 |  |  | RT46 | M3 Prod - Additional Roles for "Work Order Reporting" selection | Business needs the below roles to have access to “Work Order Reporting” selection. This is for having the search condition “Transition users” part of the selection as we need this for reporting and pulling individual stats. The “Transition Users” was removed from our RMT search for the performance speed issue. Users to be added: RT46 RMT Supervisor tier 1, RT46 RMT Supervisor tier 2, RT46 RMT SME, RT46 RMT Superuser. | This access has been applied to the additional roles supplied by business. | Zaheer, Vishek, Jadyn
8 | WBM3QA-1135 | INC6060649 | FML-5069 | Config |  | RT46 | ACB Payments | The users were using an incorrect process to add Order Items that do not have contract Cost Centre. | The system will force users to add Order Items that have contract Cost centres. | Carmen Abdrabu
9 | WBM3QA-1137 | INC5958115 | FML-4961 |  | Pass | BOTH | Purchase Invoice Posting Date to be added to "Find Supplier Invoices" Selection | A colunm was missing in the Find Purchase Inovice selection | The missing column to be added in Find Purchase Inovice selection.
10 | WBM3QA-1144 | INC6049589 | FML-5153 |  | Pass | RT46 | M3 PROD- ADDITIONAL STATUS REQUIRED ON ASSESSMENT ORDERS | We requires an additional status on Miles which should 'Unable to conduct inspection' as the status which we are currently using now is “ Further information needed “ but this is not working for us as the call center uses this status as well. We require this status as we will be using it to calculate SLA and also follow up and ensure that we track these inspections if the vehicle was not made available. | For better control on the assement order process an additional status on Miles 'Unable to conduct inspection' has been added. | Senthan, Peter
11 | WBM3QA-1145 | INC6060658 | FML-5068 | Config |  | CORP | Tax Invoice Monthly 21st. | The job was running over 10 hours. | The job will now run for 6 hours or less. | Config Team
12 | WBM3QA-1151 | INC5983665 | FML-5001 |  | Pass | BOTH | Recharge Amount is Null on Work-Order resulting in incorrect Chargeback Amount | The request is for the recharge amount to automatically equal the total cost column (ex-VAT) when the values have been inputted by the call center user to ensure the recharge amount equals the total cost. If this can be added as a validation rule when the calculate button is pressed or in a similar process it would be much appreciated. | @Nealan to provide more context please | Nealan to confirm
13 | WBM3QA-1153 | INC6001975 | FML-5015 |  | Pass | RT46 | M3 Prod - Additional "Suppliers Quote" in TO & AO Not Working Correctly | The new selection “Suppliers Quote” for AO & TO were added but the issue now is that agents would use it to attach the quote but that same quote would not showing in the “attachments” tab when sending out a document. | Reason users do not see the attached document imported against Suppliers Quote is because the current import template exists against the ‘order’ object and users are not trying to add this attachment to a document on transport/assessment order (hence different object). We’ve deactivated the existing ‘Suppliers Quote’ import template and created two new ones (one for TO and one for AO). This should allow users to select the document attached against the template when sending out a document. | Zaheer, Vishek, Jadyn
14 | WBM3QA-1156 | INC6078465 | FML-5082 |  | Pass | RT46 | M3 PRODUCTION / USER ROLES ACCESS / MANUAL SELECTION OF STATUSES ON ASSESSMENT ORDERS - JIRA (atlassian.net) | 1.RT46 RMT Inspector Supervisor, RT46 RMT Inspector Administrator and RT46 RMT Inspector Technical Advisor roles should only have access to change the status from “Email sent to inspector” to the new status “Unable to conduct inspection “. 2.We should also have access to changes status from “Email sent to inspector” back to "Draft" when we need to re-allocate inspection request that were not allocated to the correct inspector. | Adjustments to call centre secific roles in order to not be able to select assesment order statuses manually but rather driven through system process. | Senthan, Peter | Linked to ticket WBM3QA-1144
15 | WBM3QA-1160 | INC6017729 | FML-5037 |  |  | RT46 | M3 Prod- Merchants Department- Cannot create or update merchant codes | When creating or updating a supplier profile we are unable to populate or update the merchant code. | Adjustment to merchant roles in order for them to be able to add the AC Merchant code | Chanel, Vishek, Arthi
16 | WBM3QA-1162 | INC6146185 | FML-5183 |  | Pass | RT46 | M3 Prod - Work Allocation Engine (WAE) manual change report | We require a report showing all WO where the WAE assigned a supplier and the user went and cleared / deleted the allocated supplier in the supplier field and selected their own and saved it without pressing the reassign button. | Created a specific selection that can be pulled by business to show whom in the call centre is overridding the WAE. This will help for better control over allocations. | Zaheer, Vishek, Jadyn | Linked to ticket WBM3QA-1142
17 | WBM3QA-1163 | INC6060665 | FML-5067 |  |  | RT46 | On modify contract error received SofBoException 111 with arguments Get¦SofDataTypeArray because index 0 is out of bounds | When trying to modify a contract with an Administrative Transfer the following error appears. SofBoException 111 with arguments Get¦SofDataTypeArray because index 0 is out of bounds. This does not happen on every contract, just a few, but prevent the movement of vehicles between cost centres. | There was a back-end code fix to resolve this issue. Users are not expecting to not get error when modifying contract on Miles for RT46. | Theresa, Sharona
18 | WBM3QA-1164 | INC6060671 | FML-5066 |  | Pass | RT46 | M3 Prod - Exclude RT46/SAPS contracts from 'Schedule to Master Agreement' job | In production, job id 500039 ‘Schedule to master agreement’ is triggered on daily basis as part of batch plan ‘Daily Jobs’. The job generates and send out the ‘Schedule to Master Agreement’ to the customer’s fleet manager for any operating lease / fleet managed contract activated during the day. RT46 and SAPS contracts should be excluded from this job. | Removed the RT46 and SAPS JV for the specific Dialy Job, thus removing SAPS/RT46 customers (fleet managers) from receiving the Master Agreeement report. | Theresa, Sharona
19 | WBM3QA-1168 | INC6060679 | FML-5065 |  | Pass | RT46 | Prod - We need to change the quotation template for SAPS and RT46 to make the cost centre a mandatory field to insert | We have picked up that some users “miss” the cost centre when loading new quotes.. therefore, contracts and then it’s missing on the FV itself. When billing is run then those specific transactions are not billed as the cost centre was missed. We spoke to doing a small change on the quotation template via quotation template rule for every RT46 contract there should be a cost centre. The Agents would have this information at the time of loading the quote so hence, the quotation template rule change seems to be the most logical. | Have put a validation on the unit account (cost centre) field for RT46 and SAPS quotation templates. Therefore making it a mandatory field when loading new RT46 and SAPS contracts | Theresa, Sharona
20 | WBM3QA-1173 | INC6060684/ INC6060830 | FML-5064 |  | Pass | RT46 | Prod - RT46 Manual Supplier Selection - It seems like some supplier might be missed by the Selection or Custom SQL | The RT46 Manual Supplier Selection, it seems like some supplier might be missed by the Selection or Custom SQL. | Updated the SQL to ensure HDI rating of 0% is picked up byt the selection | Zaheer, Vishek, Jadyn | The fix works in Everest Perf but not in Everest QA.
21 | WBM3QA-1174 | INC6060691 | FML-5063 |  |  | RT46 | M3 Prod - Hard Block with Supplier Labour Rate Lookup Table on Work Order | We are getting an error when validating a claim, cannot find a workorder for this. There is data on the lookup table for this particular supplier. | The Order Date field is now a mandatory field on the order | Zaheer, Vishek, Jadyn
22 | WBM3QA-1175 | INC6060841 | FML-5054 |  | Pass | RT46 | Prod - The Transmission Date seems to not be updating as the order progresses through the workflow | We have received some feedback from the customer regarding the transmission dates populating on all the documents they are receiving (Pre-Auth, Clearance, Authorisations etc.). It seems like the date does not update on the document as to showcase the order moving through the different statuses, therefore giving the customer no indication of movement on their request. Under further investigation it doesn’t seem like the transmission dates are updating in accordance with the order. | Have updated all the documents so that the transmission date is now the date / time that the document is created. This will provide the date the order progresses through the workflow. | Zaheer, Vishek, Jadyn
23 | WBM3QA-1177 | INC6024257 | FML-5156 |  |  | BOTH | Remove ability for Users to manually change Purchase Invoice status (using the dropdown) | The request is for the system to no longer allow users to manually change the invoice status which would force them to use the process buttons which will ensure the correct validations to take place. (highlighted in red, functionality to be removed). We would also like the Invoice Number to not extract any information from a work-order when a new invoice is created (highlighted in yellow, functionality to default). | Adjustment to finance roles in order for them to not be able to use the dropdown
24 | WBM3QA-1178 | INC6058031 | FML-5051 |  | Pass | RT46 | User to receive message to set RT46 Contract Termination Date to End-of-Month - JIRA (atlassian.net) | In order to prevent the system from pro-rating the RT46 admin fee when a contract is terminated during a month (which impacts MVP-1 and MVP-2 specific jobs) the request is for a system message to inform the user to set the termination date to the last day of the month to ensure no pro-rating occurs.
25 | WBM3QA-1180 | INC6060742 | FML-5061 |  |  | RT46 | Prod - Clearance Document not pulling in the correct Email Contacts from Customers (eg. SAPS) | The customers are complaining that the clearance document only goes out to one SAPS contact intead of all list NSO per garage. | Now when manually sending out the clearance request, then document handling logic will pick up all 'RMT User' contacts linked to the SAPS Garage of the WO. Clearance request document handling updated on both WO and TO. Make sure to test sending via code and manual on WO. | Zaheer, Vishek, Jadyn
26 | WBM3QA-1186 | INC6138419 | FML-5170 |  | Pass | RT46 | M3 Prod - Tracking document populating incorrect pre-auth number - JIRA (atlassian.net) | The tracking document is populating the order id number in the pre-authorisation field which differs from the pre-auth document, this has caused and issue with payments and has posed a risk to business. Please may we have the “Work Order Number (Pre-Auth)” populate on both documents. | Have updated the WO Pre-Authorisation Tracking document so that the pre-authorisation number is the same in both parts. One number, therefore no confusion for the customer | Zaheer, Vishek, Jadyn
| WBM3QA-1189 | INC6138894 | FML-5171
27 | WBM3QA-1197 | INC6120171 | FML-5152 |  |  |  |  | Merchants' Administrator & Supervisor/ RMT Administrator/ RMT Inspector Supervisor/ Finance Executive roles changes: Merchants' Administrator - Bank status on supplier screen. Merchants' Administrator - Remove Competencies. Merchants' Supervisor - Remove on lookup tables. Procurement Administrator - Remove Confirm button for Lookup tables. RMT Administrator - Removing Is valid on Cost center - Check box Registration screen. RMT Inspector Supervisor - Change supplier contact details. RMT Administrator - Removing Edit access to the distance registration. Finance Executive - Access to GL entries.
28 | N/A | INC5621108 | FML-4546 |  |  | CORP | SU ACC SALES COSTS job still not running | Please note that the job "SU ACC SALES COSTS" is not running for all vehicles sales. Attached is the list of vehicles affected for April - May 2023. This issue continues to occur despite the previous fix implemented | The only ‘change’ is the name of the asset group. It seems like ‘someone’ has overwritten the asset group name in production (‘KH58XZGP’ was added), so the only thing this XML does is setting the name back to the original value ‘ACC Operating Lease Asset’ (without the KH58XZGP in it). | Martinius Boshof
29 | N/A | INC5869972 | FML-4987 |  |  | BOTH | Forklifts loaded in hours but mileage was captured in kms WBM3QA-1034 | Whenever i try open the vehicle profiles, I get the attached error. The affected reg numbers are BT7699 and 9A214599 | Tested with Liviwe and is working - 14.09.23 | Liviwe Ngquseka | This was tested with Liviwe - 14.09.23
30 | N/A | N/A | FML-4414 |  |  | CORP | TPSC:File Imports - Import Licensing Details from Certrack | File Imports - Import Licensing Details from Certrack Description: 2023-05-31 certrack upload |  | Nicolene Portgeter | No testable as it is an action.
31 | N/A | INC5914629 | FML-4901 |  |  | BOTH | Weekly DiskDrive upload failed, to investigate and rectify so that upload is successful. | Weekly DiskDrive upload failed, to investigate and rectify so that upload is successful. |  | Jarrod De Wet
32 | N/A | INC5217546 | FML-4638 |  |  | CORP | UNABLE TO MODIFY CONTRACT NO. 1000120519 | During our business meeting earlier this week, we explained to Edith and Awonke about the July FNB Insurance Renewal Order extract and its reconciliation with June. We found a few contracts where the FNB Lease Price was Zero. These are about 18 contracts in number and can be easily fixed manually. |  | Mahlatse Gwangwa
33 | N/A | INC5771003 | FML-4616 |  |  | CORP | JASPER: Please add exterior colour on the schedules | Schedules are only showing interior colour, the clients need to see the exterior colour on the schedules and not interior colour. | This was tested by Dalita and its working - 14.09.23 This has been tested by Dalita and Sandy - 18.09.23 - Working / Passed SANDY NAIDOO | Dalita Tshabalala
BAU Tickets that as NOT ready for Production
# | Sofico Jira # | INC # | FML # |  |  | RT46/ CORP/ BOTH | Description | Issue Description | Resolution | Business User | Comments
1 | N/A | INC5971331 | FML-4995 |  |  | BOTH | Please restore my user role to - Finance Executive | Please restore my user role |  | Martinius Boshof | This Resolved, in Production already
2 | N/A | INC5811819 | FML-4668 |  |  | BOTH | EP:Please investigate why Deals 5025463 & 5025473 for RCL FOODS CONSUMER (PTY)LTD (5000502) increased. | Please investigate why Deals 5025463 & 5025473 for RCL FOODS CONSUMER (PTY)LTD (5000502) increased. Liviwe Ngquseka (W5595258) did an administrative transfer, to move deals to a cost centers. | Hi All Changes approved. Business impact – Accuracy and time consuming. Regards, Edith Jacobs Problem: Lease price found to be different between contract versions when Admin transfer is done. Cause: Interest rate changed between quote and when contract went live/running. The contract revision jobs did not update the net rental for the first month rental – bug created for this in service desk. But for the second month, it has corrected the net rental where it appears to be caused by Admin transfer of the contract but in actual it is the revised price with the change in interest rate which should have shown in version 1 itself. Impact: Customer invoicing incorrect for first monthly rental. Solution: To be resolved using ticket SDWBSA-415 to fix the calculation for rental for first month rental. | Samantha Peace, Liviwe Ngquseka
3 | N/A | INC5771640 | FML-4615 |  |  | CORP | TPSC: Tracker Renewal orders | Tracker Renewal orders for June and July 2023 did not generate. This blocks us from paying the supplier | Hi All Changes approved. Business impact – Accuracy and time consuming. Regards, Edith Jacobs During our business meeting earlier this week, we explained to Edith and Awonke about the July FNB Insurance Renewal Order extract and its reconciliation with June. We found a few contracts where the FNB Lease Price was Zero. These are about 18 contracts in number and can be easily fixed manually. | Edith Jacobs
4 | N/A | INC5757199 | FML-4601 |  |  | BOTH | TPSC:Unable to use the renewal order to pay supplier invoices | Users affected W3587665 W5158869 W5421144 W5666635 W5378508 W5135788 W5287561 W5287472 W5407540 W3562751 W3562573 | Hi All Changes approved. Business impact – Accuracy and time consuming. Regards, Edith Jacobs During our business meeting earlier this week, we explained to Edith and Awonke about the July FNB Insurance Renewal Order extract and its reconciliation with June. We found a few contracts where the FNB Lease Price was Zero. These are about 18 contracts in number and can be easily fixed manually. | Edith Jacobs
5 | N/A | INC5543463 | FML-4464 |  |  | CORP | TPSC: Renewal incomplete | The attached units does not pull into Tracker renewal. Resulting in a short payment | Hi All Changes approved. Business impact – Accuracy and time consuming. Regards, Edith Jacobs During our business meeting earlier this week, we explained to Edith and Awonke about the July FNB Insurance Renewal Order extract and its reconciliation with June. We found a few contracts where the FNB Lease Price was Zero. These are about 18 contracts in number and can be easily fixed manually. | Edith Jacobs
6 | N/A | INC4705048 | FML-3725 |  |  | CORP | TPSC: Vehicle registrations not pulling into Renewal Orders | Vehicle registrations does not pull into Renewal Order 5019760 - contract reference under Find Fleet Vehicle menu | Hi All Changes approved. Business impact – Accuracy and time consuming. Regards, Edith Jacobs During our business meeting earlier this week, we explained to Edith and Awonke about the July FNB Insurance Renewal Order extract and its reconciliation with June. We found a few contracts where the FNB Lease Price was Zero. These are about 18 contracts in number and can be easily fixed manually. | Edith Jacobs
7 | N/A | INC4589948 | FML-3625 |  |  | CORP | TPSC: Certrack: Telematics Renewal Orders not generating for CarTrack and CTrack Fleet) | Telematics Renewal orders for the below suppliers not running Cartrack CTrack Fleet Management | Sign was given today by Daniel Maans - 14.09.23Hi Mandla, I tested on QA and the selection is working perfectly. This selection links to FML-3625. Thanks Everyone. This is not working - I tested on both QA and Preprod - SANDY | Edith Jacobs | Resolved and in Production already
8 | N/A | INC5161027 | FML-4084 |  |  | CORP | TPSC: Units Not Pulling Into Renewal | For further info on this incident, please contact Edith Jacobs: JacobsE@wesbank.co.za When we compare the billing from the supplier and our renewal, it does not balance, however, the units are running and in use on Miles. To avoid this error, orders are manually added as we will not be able to pay the supplier for these units Every month, the attached units are manually added to Tracker renewal order, which is time consuming | Hi All Changes approved. Business impact – Accuracy and time consuming. Regards, Edith Jacobs During our business meeting earlier this week, we explained to Edith and Awonke about the July FNB Insurance Renewal Order extract and its reconciliation with June. We found a few contracts where the FNB Lease Price was Zero. These are about 18 contracts in number and can be easily fixed manually. | Edith Jacobs
9 | N/A | INC5080431 | FML-3988 |  |  | CORP | TPSC:Renewal order is pulling out duplicate vehicles registration. | Renewal order is pulling out duplicate vehicles registration. I manualy have to remove and Amend amounts. | Hi All Changes approved. Business impact – Accuracy and time consuming. Regards, Edith Jacobs | Jane Booi | This change was tested with User Jane and not working. Mandla sent an email to Shivam-19.08.23
10 | N/A | INC4978013 | FML-3947 |  |  | CORP | TPSC:Certrack: Miles Extract on LTC - Find Licensing details and validations from Certrack for all contracts - to include date and time stamp | This report is used to validate the transactions that were uploaded via the certrack file. The problem is that it shows all contracts and not just the vehicles that were in the certrack file. It then makes validating the data extremely difficult. The suggestion is to add the date and time stamp to the extract and as a condition on the extract. |  | Nicolene Portgeter
11 | N/A | INC5731896 | FML-4732 |  |  | CORP | CR:Incorrect Credit Risk amount - current exposure | The credit risk amount is incorrect – the facility was approved for R 2 million, which was loaded on Miles. The client had one draw down of R 1 million, however Miles shows the existing exposure as R 838 939 – see screenshots of the running LTC below; I am busy with renewing the facility, but the credit team needs the existing exposure to read correctly. |  | Ranelle Reddy
12 | N/A | INC5830210 | FML-5000 |  |  | CORP | Incorrect contract link to FV and business does not have the minus(-) button to remove it. Please remove LTC 5024084 as per the screen prints. | FV - LG15FYGP FV - LG15GCGP |  | Daniel Maans | To be removed
13 | N/A | INC5485019 | FML-4740 |  |  | BOTH | Miles auto accrual journal is not reversing | I just had a high-level view of the accrued Eppenses GL accounts on Miles, specifically the 22811014565 accounts. So, for background, Miles accounts for VAPS income every month when billing occurs, and then when a work order and invoice is loaded and posted on the system, the amount goes to VAPS expense. Therefore, ideally the income should match the expense since we collect VAPS from customers and pay them over to suppliers. So, each month, the system expects that a VAPS income will be collected, and VAPS expense paid over, so when these don't match, Miles generates an automatic journal to accrue for VAPS expenses equal to VAPS income collected and not paid over. This journal is posted automatically each last day of the month and reversed in the new month. However, it looks like since December 2022, Miles has not been processing the accrual reversals as expected, which led to the balance in the GL account equaling R24m. I highlighted red to show that there were no "SU Accrual Reversal" entries in the months indicated. | This was tested by Tinus Boshoff and he has given sign off - 14.09.23. Sent the email to Mandla. I have retested on Pre-Prod and its working -PASSED 18.09.2023. Tested on QA and Preprod and signed off by QA and Martinus. Sign off attached on Jira together with my test results - 19.09.23 (Sandy Naidoo) | Nyiko Chuma | To be removed
14 | N/A | N/A | FML-4661 |  |  | BOTH | TPSC:FNB Renewal for July not pulling on miles. | Refresh Non-Production Miles Environments - Data Migration Description: FNB Renewal for July not pulling on miles. | I | Awonke Mama
16 | N/A | INC5540475 | FML-4443 |  |  | CORP | Shoprite Checkers Miles Cost Centres Duplicated | We have a massive exercise to undertake in correcting the description of Shoprite Cost Centers. The issue however is that Cost Centers reflect as duplicated on Miles SC screen. This prevents us from making any changes as we are unsure of which cost center the vehicles may be loaded on, furthermore, this has a great impact on Shoprite Checkers Billing. |  | Klyne Poliah
17 | N/A | INC5870167 | FML-4799 |  |  | CORP | DC:File creation failed | Please investigate why the invoice caused the batch to stop |  | Edith Jacobs | To be closed
18 | N/A | INC5644699 | FML-4574 |  |  | CORP | Require the ability to generate an Early Settlement letter with all the correct values | Problem Statement/Opportunity When initiating a fleet vehicle leasing contract, the total revenue that will be recovered at the end of the contract is pre calculated. This amount must be recovered regardless of whether there is an early settlement by the customer or not. The current issue experienced is that where a customer/client requests for their vehicle contract to be terminated earlier (e.g., 3/6 months or more) a settlement quote must be sent to them for acceptance. However, it has been raised by customers that subsequent to paying the settlement amount as quoted on the settlement letter, they still receive statements from WB stipulating that they still have outstanding charges, these could either be future billings or previous rentals not paid. There was no consistent application of what should be included in the settlement value provided to the customer and the system settlement letter was often adjusted to include arrear rentals. This causes issues for both the client and business since there are numerous complaints which are received from clients stating that they have been provided with an amount that they have subsequently paid however they are still being charged for other amounts over and above what has been paid. Future arrears will still be settled, and the customer is liable to pay for them. The solution for the stipulated business problem is that going forward when a client requests for an early settlement for their vehicle contract, the settlement letter must include all of the future billings which can be calculated using the initial contract agreement amount. The settlement letter will not include arrear rentals and the system generated settlement letter will be used. |  | Deneshan Pillay
19 | N/A | INC5536353 | FML-4895 |  |  | CORP | FLEET LIST:The following vehicle KH58XZGP is on the Fleet list but not on the FA register, upon investigation it looks like OPL deal on Miles has no allocated values .The | The following vehicle KH58XZGP is on the Fleet list but not on the FA register, upon investigation it looks like OPL deal on Miles has no allocated values. The same vehicle also has a Managed Maintenance attached to it. |  | Jan Nyiko Chuma
20 | N/A | INC4589948 | FML-3625 |  |  | CORP | TPSC: Certrack: Telematics Renewal Orders not generating for CarTrack and CTrack Fleet) | Telematics Renewal orders for the below suppliers not running Cartrack CTrack Fleet Management | Sign was given today by Daniel Maans - 14.09.23Hi Mandla, I tested on QA and the selection is working perfectly. This selection links to FML-3625. Thanks Everyone. | Edith Jacobs
EP5 Tickets
# | Sofico Jira # | INC # | FML # |  |  | Function | Description | Issue Description | Resolution | Business User | Comments
1 | WBRT46-321 | INC6060754 |  |  |  | RT46 | SAPS Jobcard file Enhancement (EP) - JIRA (atlassian.net) | Currently, SAPS sends a file with individual JobCard A batch picks up the file every 30 minutes and process on Miles Global Scape(file transfer) mechanism is in use to transfer the file from SAPS into WesBank environment SAPS wants to be able to send mulitple jobcards in a single file. | SAPS should now be able to send multiple JobCards in one file, there is no change in the file layout as per the existing/current file. The connector in place has been enhanced. |  | 12/09- New xml to be applied 13/09- Tested and passed
2 | WBM3QA-1033 | INC6060778 |  |  |  | BOTH | Benchmark pricing to pull per make and model - PostGoLive CCN (EP5) | Benchmark pricing to be fixed by per make and model currently it is pulling by make showing multiple models parts when looking for a specific benchmarked price | The proposed changes to link the MAPO baskets should be linked to the GMV code. Was done as a three parter (1 - Adding GMV codes to catalog parts, 2 - Updating the description of catalog parts, 3 - Updating benchmark price on WO) |  | 12/09- Ticket sent back to Sofico.
3 | WBM3QA-1062 | INC6060785 |  |  |  | RT46 | M3 Prod - System is not removing the existing Merchant after disapproving the Order (EP5) | After assigin a supplier, if the agent disapproves that specific order/supplier, when reallocating a new merchants needs to be selected by the WAE. | Internal Sofico Dev ticket thus not sure exactly what fix was implmented. But need to now make sure that after disapproving the order and a new one is created that the same disapproved merchant is selected. |  | Tested in the wrong environment. To be re-tested.
4 | WBM3QA-1093 | INC6060807 |  |  | Passed | RT46 | M3 Prod - Mandate lookup Table using Total Amount Excluding VAT instead of +VAT - CCN (EP5) | When the system validates a claim it uses the total amount excluding VAT instead of the amount +VAT. As seen below. The mandate is set at 15k, the claim is below the mandated amount excluding VAT and would not ask for a clearance request where as the amount is actually over 16k including VAT and a request for customer clearance should come up. After validating the claim is moves to “mandates are validated”. In the case of the supplier being NON VAT liable this would work fine with no issues. | Internal Sofico Dev ticket thus not sure exactly what fix was implmented. However, now the validation should be done on the total VAT inclusive price.
5 | WBM3QA-1142 | INC5968987 |  |  | Passed | RT46 | M3 - Prod - User overriding WAE assigned supplier (EP5) | The users are able to override the assigned WAE supplier. Risk: users are able to select their own suppliers and override the WAE which is against the agreements. This results in too many orders at one supplier, bay capacity override and unfair advantage to suppliers. | When changing the supplier manually and click on Assign Supplier, blocking error message is now displayed.
8 | SDWBSA-384 |  |  |  |  | ? | Miles Hanging - Sofico Service Desk |  |  |  | No QA required. Nkosinathi to assist how best to test it.
9 | SDWBSA-412 |  |  |  |  | ? | Miles Direct Debit Load Report Import error - Sofico Service Desk |  | File was not picked up by Ebus
10 | SDWBSA-415 |  |  |  |  | ? | Interest rate change not reflected after customer invoicing jobs are executed Sofico Service Desk |  |  |  | BAU ticket-data related
11 | SDWBSA-416 |  |  |  |  | ? | Calculate early payment discounts - Sofico Service Desk |  |  |  | ACB related production issue caused by data. Closed.

## September Deployment
| FML-5164 = WebLogic | FML-5163 = XMLs | FML-5165 = Database
Ready for Production in September 2023
# | Sofico Jira # | INC # | FML # | DI tickets | Description | Issue Description | Resolution | Business User | Comments
1 | WBM3QA-939 | INC6060608/ INC6060767/ INC6057901 | [FML-5151] | [FML-5163] | M3 & Corp - On Accident Pre-inspection does not validate when cost and Recharge amount is captured - GoLive | In Pre-Inspection process, the system needs to validate any recharge and cost amounts when uploading Final Inspection by Call Centre. | When entering in a value on the assesment order, there is a validation that is run, and if a vlue is seen a hard block/error message prompts the agent to remove the rand value. | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli, Warren Naidoo | PASSED
2 | WBM3QA-945 | INC6060633 | [FML-5071] | [FML-5163] | M3 - Data Integration - When a merchant is selected, a validation is needed on Draft --> Pre-Authorisation status change to ensure that a supplier that has been allocated has RT46 Agreement = TRUE | When a merchant is selected (whether manual selection or via the WAE), a validation is needed on order status “Pre-Authorisation” status to ensure that specific supplier that has been allocated is RT46 Agreement = TRUE. This validation will be triggered when the status changes from Draft → Pre-Authorisation. | The solution here is validation on all RT46 orders when a merchant has been assigned or selected. The validation checks that the specifc merchant/supplier has the RT46 Agreement ticked (TRUE). If not, the Hard Block error is displayed. | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli | PASSED - Blocker coming up when trying to assign non RT46 supplier
3 | WBM3QA-983 | INC6017731 | [FML-5036] | [FML-5163] | M3 - Bypass the Required Documents to Activate Supplier - PostGoLive | Business needed a solution to bypass the Required Documents to Activate Supplier (all 9 documents) for manual onboarding of merchants received from FlowCentric post go live. This will reduce the turnaround time for merchant onboarding by merchant department and will help in processing the onboarding. | For the onboarding of RT46 merchnats, the document storage for their onboarding document are still FLowCentric, therefore to alleviate doc storage on Miles, there is a bypass on the comulary documents to be uploaded for new RT46 merchants being loaded. | Chanel Saunders, Lita Gibe, Arthi Moodley | PASSED
4 | WBM3QA-1075 | INC6017658 | [FML-5040] | [FML-5163] | CORP - Main Repair Order switching to OPL contract when loading accident claims | When navigating from RMT ribbon into Incident/Accident order, the system defaults to the OPL contract instead of MM contract. |  | Travis Padachy, Warren Naidoo | PASSED
5 | WBM3QA-1109 | INC6060642 | [FML-5070] | [FML-5163] | M3 Selections- Merchants Dept - We need to be able to pull reports. | Buness needs to pull a report on all merchants brought into Miles with no RT46 agreement and once off supplier tick. Reports must contain the Auto Card Merchant codes and addresses along with the other detail that already populates. When pulling reports on work orders, to track allocations to merchants between specific date ranges, we are unable to pull this report between specified timelines for example jobs allocated in the past 7 days or month to date/year to date etc. Currently we can only pull a full report not specifying the date however this report is too large to be downloaded/extracted. | The ability to pull reports granted to those specific roles | Chanel Saunders, Lita Gibe, Arthi Moodley | PASSED
6 | WBM3QA-1125 | INC5943653 | [FML-5038] | [FML-5163] | M3 Prod - SAPS TO + TRACKING is being sent to supplier instead of a Customer | The TO SAPS + TRACKING document gets sent to the Supplier instead of it being sent to the Customer. | The document mapping for the respective emails addresses have been updated to pull the correct email address. For SAPS, the linked WO will provide the MT users linked to the SAPS Garage. | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli | PASSED - As per screenshot, no supplier email populating in tracking document.
7 | WBM3QA-1131 | INC6001989 | [FML-5016] | [FML-5163] | M3 Prod - Additional Roles for "Work Order Reporting" selection | Business needs the below roles to have access to “Work Order Reporting” selection. This is for having the search condition “Transition users” part of the selection as we need this for reporting and pulling individual stats. The “Transition Users” was removed from our RMT search for the performance speed issue. Users to be added: RT46 RMT Supervisor tier 1, RT46 RMT Supervisor tier 2, RT46 RMT SME, RT46 RMT Superuser. | This access has been applied to the additional roles supplied by business. | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli | PASSED - As per scheenshot, selection is available.
8 | WBM3QA-1135 | INC6060649 | [FML-5069] | [FML-5163] | ACB Payments | The users were using an incorrect process to add Order Items that do not have contract Cost Centre. | The system will force users to add Order Items that have contract Cost centres. | Carmen Abdrabu
9 | WBM3QA-1137 | INC5958115 | [FML-4961] | [FML-5163] | Purchase Invoice Posting Date to be added to "Find Supplier Invoices" Selection | A colunm was missing in the Find Purchase Inovice selection | The missing column to be added in Find Purchase Inovice selection. | Nealan Michaels | PASSED
10 | WBM3QA-1144 | INC6049589 | [FML-5153] | [FML-5163] | M3 PROD- ADDITIONAL STATUS REQUIRED ON ASSESSMENT ORDERS | We requires an additional status on Miles which should 'Unable to conduct inspection' as the status which we are currently using now is “ Further information needed “ but this is not working for us as the call center uses this status as well. We require this status as we will be using it to calculate SLA and also follow up and ensure that we track these inspections if the vehicle was not made available. | For better control on the assement order process an additional status on Miles 'Unable to conduct inspection' has been added. | Senthan Nadasen, Peter Zacheus | PASSED
11 | WBM3QA-1145 | INC6060658 | [FML-5068] | [FML-5163] | Tax Invoice Monthly 21st. | The job was running over 10 hours. | The job will now run for 6 hours or less. | Config Team
12 | WBM3QA-1151 | INC5983665 | [FML-5001] | [FML-5163] | Recharge Amount is Null on Work-Order resulting in incorrect Chargeback Amount | The request is for the recharge amount to automatically equal the total cost column (ex-VAT) when the values have been inputted by the call center user to ensure the recharge amount equals the total cost. If this can be added as a validation rule when the calculate button is pressed or in a similar process it would be much appreciated. |  | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli | PASSED - rechange amount now auto populated even when you removed it, save and them validate or approve.
13 | WBM3QA-1153 | INC6001975 | [FML-5015] | [FML-5163] | M3 Prod - Additional "Suppliers Quote" in TO & AO Not Working Correctly | The new selection “Suppliers Quote” for AO & TO were added but the issue now is that agents would use it to attach the quote but that same quote would not showing in the “attachments” tab when sending out a document. | Reason users do not see the attached document imported against Suppliers Quote is because the current import template exists against the ‘order’ object and users are not trying to add this attachment to a document on transport/assessment order (hence different object). We’ve deactivated the existing ‘Suppliers Quote’ import template and created two new ones (one for TO and one for AO). This should allow users to select the document attached against the template when sending out a document. | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli | PASSED - As per screenshot, "suppliers quote" is selectable for both AO & TO.
14 | WBM3QA-1156 | INC6078465 | [FML-5082] | [FML-5163] | M3 PRODUCTION / USER ROLES ACCESS / MANUAL SELECTION OF STATUSES ON ASSESSMENT ORDERS - JIRA (atlassian.net) | 1.RT46 RMT Inspector Supervisor, RT46 RMT Inspector Administrator and RT46 RMT Inspector Technical Advisor roles should only have access to change the status from “Email sent to inspector” to the new status “Unable to conduct inspection “. 2.We should also have access to changes status from “Email sent to inspector” back to "Draft" when we need to re-allocate inspection request that were not allocated to the correct inspector. | Adjustments to call centre secific roles in order to not be able to select assesment order statuses manually but rather driven through system process. | Senthan Nadasen, Peter Zacheus | PASSED
15 | WBM3QA-1160 | INC6017729 | [FML-5037] | [FML-5163] | M3 Prod- Merchants Department- Cannot create or update merchant codes | When creating or updating a supplier profile we are unable to populate or update the merchant code. | Adjustment to merchant roles in order for them to be able to add the AC Merchant code | Chanel Saunders, Lita Gibe, Arthi Moodley | PASSED
16 | WBM3QA-1162 | INC6146185 | [FML-5183] | [FML-5163] | M3 Prod - Work Allocation Engine (WAE) manual change report | We require a report showing all WO where the WAE assigned a supplier and the user went and cleared / deleted the allocated supplier in the supplier field and selected their own and saved it without pressing the reassign button. | Created a specific selection that can be pulled by business to show whom in the call centre is overridding the WAE. This will help for better control over allocations. | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli | PASSED - Linked to ticket WBM3QA-1142.
17 | WBM3QA-1163 | INC6060665 | [FML-5067] | [FML-5163] | On modify contract error received SofBoException 111 with arguments Get¦SofDataTypeArray because index 0 is out of bounds | When trying to modify a contract with an Administrative Transfer the following error appears. SofBoException 111 with arguments Get¦SofDataTypeArray because index 0 is out of bounds. This does not happen on every contract, just a few, but prevent the movement of vehicles between cost centres. | There was a back-end code fix to resolve this issue. Users are not expecting to not get error when modifying contract on Miles for RT46. | Theresa Hughes, Sharona Panday, Julie Claassen | PASSED
18 | WBM3QA-1164 | INC6060671 | [FML-5066] | [FML-5163] | M3 Prod - Exclude RT46/SAPS contracts from 'Schedule to Master Agreement' job | In production, job id 500039 ‘Schedule to master agreement’ is triggered on daily basis as part of batch plan ‘Daily Jobs’. The job generates and send out the ‘Schedule to Master Agreement’ to the customer’s fleet manager for any operating lease / fleet managed contract activated during the day. RT46 and SAPS contracts should be excluded from this job. | Removed the RT46 and SAPS JV for the specific Dialy Job, thus removing SAPS/RT46 customers (fleet managers) from receiving the Master Agreeement report. | Theresa Hughes, Sharona Panday | PASSED, tested by Config team.
19 | WBM3QA-1168 | INC6060679 | [FML-5065] | [FML-5163] | Prod - We need to change the quotation template for SAPS and RT46 to make the cost centre a mandatory field to insert | We have picked up that some users “miss” the cost centre when loading new quotes.. therefore, contracts and then it’s missing on the FV itself. When billing is run then those specific transactions are not billed as the cost centre was missed. We spoke to doing a small change on the quotation template via quotation template rule for every RT46 contract there should be a cost centre. The Agents would have this information at the time of loading the quote so hence, the quotation template rule change seems to be the most logical. | Have put a validation on the unit account (cost centre) field for RT46 and SAPS quotation templates. Therefore making it a mandatory field when loading new RT46 and SAPS contracts | Theresa Hughes, Sharona Panday, Julie Claassen | PASSED
20 | WBM3QA-1173 | INC6060684/ INC6060830 | [FML-5064] | [FML-5164] | Prod - RT46 Manual Supplier Selection - It seems like some supplier might be missed by the Selection or Custom SQL | The RT46 Manual Supplier Selection, it seems like some supplier might be missed by the Selection or Custom SQL. | Updated the SQL to ensure HDI rating of 0% is picked up byt the selection | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli | PASSED - Table is pulling suppliers info with a value greater then 0.
21 | WBM3QA-1174 | INC6060691 | [FML-5063] | [FML-5163] | M3 Prod - Hard Block with Supplier Labour Rate Lookup Table on Work Order | We are getting an error when validating a claim, cannot find a workorder for this. There is data on the lookup table for this particular supplier. | The Order Date field is now a mandatory field on the order | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli | PASSED - As per screenshot, blocker appears.
22 | WBM3QA-1175 | INC6060841 | [FML-5054] | [FML-5164] | Prod - The Transmission Date seems to not be updating as the order progresses through the workflow | We have received some feedback from the customer regarding the transmission dates populating on all the documents they are receiving (Pre-Auth, Clearance, Authorisations etc.). It seems like the date does not update on the document as to showcase the order moving through the different statuses, therefore giving the customer no indication of movement on their request. Under further investigation it doesn’t seem like the transmission dates are updating in accordance with the order. | Have updated all the documents so that the transmission date is now the date / time that the document is created. This will provide the date the order progresses through the workflow. | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli | PASSED
23 | WBM3QA-1177 | INC6024257 | [FML-5156] | [FML-5163] | Remove ability for Users to manually change Purchase Invoice status (using the dropdown) | The request is for the system to no longer allow users to manually change the invoice status which would force them to use the process buttons which will ensure the correct validations to take place. (highlighted in red, functionality to be removed). We would also like the Invoice Number to not extract any information from a work-order when a new invoice is created (highlighted in yellow, functionality to default). | Adjustment to finance roles in order for them to not be able to use the dropdown | Carmen Abdrabu
24 | WBM3QA-1178 | INC6058031 | [FML-5051] | [FML-5163] | User to receive message to set RT46 Contract Termination Date to End-of-Month - JIRA (atlassian.net) | In order to prevent the system from pro-rating the RT46 admin fee when a contract is terminated during a month (which impacts MVP-1 and MVP-2 specific jobs) the request is for a system message to inform the user to set the termination date to the last day of the month to ensure no pro-rating occurs. |  | Theresa Hughes, Sharona Panday, Julie Claassen | PASSED
25 | WBM3QA-1180 | INC6060742 | [FML-5061] | [FML-5163] | Prod - Clearance Document not pulling in the correct Email Contacts from Customers (eg. SAPS) | The customers are complaining that the clearance document only goes out to one SAPS contact intead of all list NSO per garage. | Now when manually sending out the clearance request, then document handling logic will pick up all 'RMT User' contacts linked to the SAPS Garage of the WO. Clearance request document handling updated on both WO and TO. Make sure to test sending via code and manual on WO. | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli (Thuso Nwedamutswu) | PASSED
26 | WBM3QA-1186 | INC6138419 | [FML-5170] | [FML-5164] | M3 Prod - Tracking document populating incorrect pre-auth number - JIRA (atlassian.net) | The tracking document is populating the order id number in the pre-authorisation field which differs from the pre-auth document, this has caused and issue with payments and has posed a risk to business. Please may we have the “Work Order Number (Pre-Auth)” populate on both documents. | Have updated the WO Pre-Authorisation Tracking document so that the pre-authorisation number is the same in both parts. One number, therefore no confusion for the customer | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli | PASSED - as per screenshot, same pre auth number on tracking document and work order
27 | WBM3QA-1189 | INC6138894 | [FML-5171] | [FML-5164] | M3-PROD- Customer clearance documents duplicating parts and cost - JIRA (atlassian.net) | When trying to send out clearance all the parts are duplicated on the clearance including the total amount. |  | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli | PASSED
28 | N/A | INC5621108 | [FML-4546] | [FML-5163] | SU ACC SALES COSTS job still not running | Please note that the job "SU ACC SALES COSTS" is not running for all vehicles sales. Attached is the list of vehicles affected for April - May 2023. This issue continues to occur despite the previous fix implemented | The only ‘change’ is the name of the asset group. It seems like ‘someone’ has overwritten the asset group name in production (‘KH58XZGP’ was added), so the only thing this XML does is setting the name back to the original value ‘ACC Operating Lease Asset’ (without the KH58XZGP in it). | Martinius Boshof | PASSED
29 | N/A | INC5869972 | [FML-4987] | [FML-5165] | Forklifts loaded in hours but mileage was captured in kms WBM3QA-1034 | Whenever i try open the vehicle profiles, I get the attached error. The affected reg numbers are BT7699 and 9A214599 | Issue is caused by WO with multiple disapprove reasons. It’s duplicating the WO items for each of the disapprove reasons. Have updated the SQL to only get the latest disapprove reason. This stops the duplicate WO items. Updated XML file attached with new SQL. | Liviwe Ngquseka | PASSED
30 | N/A | N/A | [FML-4414] | [FML-5163] | TPSC:File Imports - Import Licensing Details from Certrack | File Imports - Import Licensing Details from Certrack Description: 2023-05-31 certrack upload |  | Nicolene Portgeter | PASSED - No testable as it is an action.
31 | N/A | INC5914629 | [FML-4901] | [FML-5163] | Weekly DiskDrive upload failed, to investigate and rectify so that upload is successful. | Weekly DiskDrive upload failed, to investigate and rectify so that upload is successful. |  | Jarrod De Wet | PASSED
32 | N/A | INC5771003 | [FML-4616] | [FML-5164] | JASPER: Please add exterior colour on the schedules | Schedules are only showing interior colour, the clients need to see the exterior colour on the schedules and not interior colour. | This was tested by Dalita and its working - 14.09.23 This has been tested by Dalita and Sandy - 18.09.23 - Working / Passed SANDY NAIDOO | Dalita Tshabalala | PASSED - Tested and Happy with the result
33 | N/A | INC5217546 | [FML-4638] | [FML-5163] | UNABLE TO MODIFY CONTRACT NO. 1000120519 | During our business meeting earlier this week, we explained to Edith and Awonke about the July FNB Insurance Renewal Order extract and its reconciliation with June. We found a few contracts where the FNB Lease Price was Zero. These are about 18 contracts in number and can be easily fixed manually. |  | Khabane Manase | FAILED. STILL UNABLE TO MODIFY CONTRACT NO. 1000120519.

## 13 October Deployment
M3 XML DI = FML-5250, M3 DBA DI = FML-5260, M3 WebLogic DI = FML-5259, Wintel Server backup = FML-5265, DBA - DB Patch DI = FML-5263, Weblogic - App Patch DI = FML-5264 BAU XML DI = FML-5260,
# | Sofico Jira # | ServiceNow # | FML # | DI# | Stream | QA Sign off Date | UAT Sign off Date | Status | Description | Issue Description | Resolution | Business User | Comments | Assignee (Config Resource) | Post production Feedback
1 | WBM3QA-1133 | INC6217078 | FML- |  | M3 | 11/10/2024 | 12/10/2024 | Passed Production sainty check | M3 Production - Admin role is able to active new suppliers and banking details dont need to be validated by Supervisor | The system allows the Merchant Department Admin roles to validate banking details and active a New supplier. New to Active - The system allows an admin role to activate a New supplier, this should not be possible, only the Supervisor or Admin Role should be able to do so. The admin role should have access to activate a supplier from any other status beside New. Banking details- when the admin role updates the banking details the "to be validated" indicator changes automatically to "open" when saving the updates, this removes the need for a Supervisor role to validate the Banking details as the "to be validated" should only be changed by the Supervisor | Role adjustment as to fit the business need | Chanel Saunders, Lita Gibe | Part of WBM3QA-1197. Deployed to Production
2 | WBM3QA-1152 | INC5981548 | FML- 4989 |  | M3 | 11/10/2024 | 12/10/2024 | Passed Production sainty check | M3 Prod - RT46 RMT Administrator Role can Edit Distance Registration | We have picked up an issue with the RT46 RMT Administrator role. they are now able to edit vehicle “Distance Registration”, this was not the case after GO Live but for some reason they are able to now. as per the role sheet it was not ticked for access and passed the negative test. please can this be changed as we cannot have an Admin agent edit the distance registration field | Role adjustment as to fit the business need | Vishek Inarman, Zaheer Sader | Part of WBM3QA-1197. Deployed to Production
3 | WBM3QA-1154 | INC5983664 | FML- 5002 |  | M3 | 11/10/2024 | 12/10/2024 | Awaiting Production sainty check |  | Chargebacks for purchase invoices that were posted after the “Update VAT Code to STDZ on Charge-on BI linked to Non Vat Liable Suppliers” had already run had the incorrect VAT posting code resulting in VAT being added to non-VAT liable invoices due to the “Charge-back invoicing” job picked up the invoices and applied the incorrect invoice type to the sales invoice. The ask is for the Charge-back invoicing job to exclude RT46 and SAPS joint-venture linked purchase invoices to ensure these invoices are processed without this error occurring again. The concern is that without a fix, these issues will likely occur each month on the 20th and potentially the 30th due to batch processes starting earlier. | ?? | Nealan Michaels | To check if it went to Prod - Nkosinathi and to get the FML number from Config.
4 | WBM3QA-1161 | INC6120171 | FML- |  | M3 | 2023-11-10 | 2023-12-10 | Awaiting Production sainty check | M3 Prod- Merchants Department- Inability to remove a competency from the lookup table | We are required to remove workshop competencies from OEM suppliers however we do not have a remove selection. Currently there is only a function to add competencies on the Supplier Competency Look-up Table | Role adjustment as to fit the business need | Chanel Saunders, Lita Gibe | Part of WBM3QA-1197. Deployed to Production
5 | WBM3QA-1185 | INC6173504 | FML - |  | M3 | 2023-11-10 | 2023-12-10 | Passed Production sainty check | Performance improvement for “Dispute and Credit Outgoing Invoice RT46 SAPS Monthly Rental” job | Performance improvement for “Dispute and Credit Outgoing Invoice RT46 SAPS Monthly Rental” job |  | Vishek Inarman, Zaheer Sader | Deployed to Production
6 | WBM3QA-1187 | INC6120171 |  |  | M3 | 2023-11-10 | 2023-12-10 | Awaiting Production sainty check | M3 Prod- Merchants - Remove ability to approve on Early Settlement Lookup Table | Merchant admin role and Merchant supervisor role must not have access to approve on the Early settlement Discount Lookup Table. Please remove this function from these roles, only Merchant and Procurement Manager Role should have this access in the Merchants Department. Merchant admin and Merchant supervisor role must be able to amend- update and populate however the approval should be for the Manger role within Procurement and Merchant Managment. | Role adjustment as to fit the business need | Chanel Saunders, Lita Gibe | Part of WBM3QA-1197. Deployed to Production
7 | WBM3QA-1188 | INC6249926 |  |  | M3 | 11/10/2023 | 12/10/2023 | Awaiting Production sainty check | M3 Prod - There is no way to distinguish between Cost Centre and Sites when link a new Contact as an RMT User on SAPS | Users are struggling when loading new RMT Users for complex customers (i.e.. complex underpinning organization structures) especially for SAPS customer. When a new Contact is created and the necessary personal info is inputted, they need to link the new contact to the specific Unit Account. However, when trying to link the specific SAPS site i.e. CRADOCK-WORKSHOP, there are actually 3 to choose from, and the User does not know which one is the Site as to correctly link the new contact. | An info bubble in placed on the unit account field to allow the user to view if the cost centre or site has been selected. This is to ensure the right RMT contact is linked to the right site and or cost cenre | Sharona Panday, Theresa Hughes Maleshoane Tabane
8 | WBM3QA-1194 | INC6245810 | FML - 5295 | FML-5250 | M3 | 11/10/2025_PASSED | 12/10/2025_PASSED | Passed Production sainty check | M3 PROD - ADDTIONAL FIELDS ON THE "INSPECTION REPORTS READY FOR REVIEW" | The call center team requires more fields on the “Inspection reports ready for review dashboard.” The required fields will be as per below. Please advise if you require any additional fields other than the ones mentioned below: *Vehicle reg *Vehicle type *Client Name | Refinement on the dahboard and slection. Additonal fields have been added to the dashboard/selection to give the team better clarity on the inspections themsleves. | Senthan Nadasen | Deployed to Production
9 | WBM3QA-1197 | INC6120171 | FML- 5152 | FML-5250 | M3 | 11/10/2026 | 12/10/2026 | Awaiting Production sainty check | Merchants' Administrator & Supervisor/ RMT Administrator/ RMT Inspector Supervisor/ Finance Executive roles changes | Merchants' Administrator - Remove Competencies Merchants' Supervisor - Remove on lookup tables. Procurement Administrator - Remove Confirm button for Lookup tables. RMT Administrator - Removing 'Is valid' on Cost center - Check box Registration screen. RMT Administrator - Removing Edit access to the distance registration. RMT Inspector Supervisor - Change supplier contact details. Finance Executive - Access to GL entries. | Role adjustment as to fit the business need Tested and Passed | Vishek Inarman, Zaheer Sader, Chanel Saunders, Lita Gibe, Daniel Maans, Senthan Nadasen, Peter Zacheus, Martinus Boshoff | Deployed to Production
10 | WBM3QA-1221 | INC6248145 | FML - |  | M3 | 11/10/2023 PASSED | 12/10/2023 PASSED | Awaiting Production sainty check | Add "Customer Name" and "Customer License Plate" to GL: Browse Allocations Selection and Results | Can the following columns please be added to the search conditions as well as outputs for the General Ledger: Browse Allocations selection: Customer Name CUstomer License Plate Supplier Name |  | Nealan Michaels
27 | N/A | INC5161027 | FML-4084 |  | BAU | 11/10/2023 | 12/10/2023 |  | TPSC: Units Not Pulling Into Renewal | TPSC: Units Not Pulling Into Renewal (Mandla Mthombeni has just added New Implementation steps on the deployment ticket - 2023/10/13 |  | Edith Jacobs | Test and passed. Test Results and user sign off added to Jira
34 | N/A | INC5540475 | FML-4443 |  | BAU | 11/10/2023 | 12/10/2023 |  | Shoprite Checkers Miles Cost Centres Duplicated | Shoprite Checkers Miles Cost Centres Duplicated |  | Klyne Poliah | Tested / Passed test results and Summary report added on Jira together with user sign off 3.10.23 |  | Sanity tested and failed-Might be a data issue
42 | N/A | INC5830210 | FML-5000 |  | BAU | 11/10/2023 | 12/10/2023 |  | Incorrect contract link to FV and business does not have the minus(-) button to remove it. Please remove LTC 5024084 as per the screen prints. | Incorrect contract link to FV and business does not have the minus(-) button to remove it. Please remove LTC 5024084 as per the screen prints. |  | Daniel Maans | Tested / passed test results and user sign off on Jira | Nkosinathi | Tested and passed Feedback received Via email
43 | N/A | INC6120171 | FML-5152 |  | BAU | 11/10/2023 | 12/10/2023 |  | Miles Roles Fixes | Miles Roles Fixes |  | Chanel Saunders, Lita Gibe, Daniel Maans, Senthan Nadasen, Peter Zacheus, Martinus Boshoff |  |  | Not Fully Tested
45 | N/A | INC5909215 | FML-4894 |  | BAU | 11/10/2023 | 12/10/2023 |  | Why can Finance Administrator - AR make changes to the payment file. | Why can Finance Administrator - AR make changes to the payment file. |  | Maya Naidoo Edit/Jane |  | Nkosinathi | Not Tested
48 | N/A | INC6179876 | FML-5222 |  | BAU | 2023-11-10 | 12/10/2023 |  | Activation type for sales admin role | Activation type for sales admin role |  | Dalita | Tested / Passed test results Report added on Jira together with user sign off 3.10.23 | Nkosinathi | Not Tested
49 | N/A | INC6206159 | FML-5243 |  | BAU | 11/10/2023 | 12/10/2023 |  | My team is getting an error when attempting to approve a Generic Order | My team is getting an error when attempting to approve a Generic Order |  | Nonhlanhla | Tested / Passed test results Report added on Jira together with user sign off 06.10.23 | Charmaine Miller / Nonhlanhla | Test failed _ Being re-looked at
| N/A | INC6197049 | FML-5246 |  | BAU | 11/10/2023 | 12/10/2023 |  | unable to terminate vehicle - JH43XVGP | unable to terminate vehicle - JH43XVGP |  | Nkosi Goodman | Tested / Passed test results Report added on Jira together with user sign off 09.10.23 |  | Tested and passed Feedback received Via email
Not deployed to Production
# | Sofico Jira # | ServiceNow # | FML # | DI# | Stream | QA Sign off Date | UAT Sign off Date | Status | Description | Issue Description | Resolution | Business User | Assignee (Config Resource) | Comments
1 | WBM3QA-1033 | INC6060778 |  |  | M3 | 20/10/2023 | 25/10/2023 | QA Testing | Benchmark pricing to pull per make and model - PostGoLive CCN (EP5) | Benchmark pricing to be fixed by per make and model currently it is pulling by make showing multiple models parts when looking for a specific benchmarked price. Baskets to be linked to the GVM codes. | When entering the quote and specific line items, when hitting calculate the specific benchmarked price will be populated by per make and model | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli, Travis Padachy, Warren Naidoo
2 | WBM3QA-1062 | INC6060785 | FML-5057 | FML-5250 | M3 | 20/10/2023 | 25/10/2023 | With Sofico | M3 Prod - System is not removing the existing Merchant after disapproving the Order (EP5) | This is for Work Orders: *Create WO for specific FV, with specific Milage. *Once approved, I disapproved, and close the specific WO. *from the SAME FV, a new WO is created, with the same Mileage. *The exact same merchant which disapproved in the previous WO gets allocated again. | Functionailty to recognise the disppaorved merchant, and not when trying to reallocate to a different merchant the same merchant isnt picked up. WAE refinement | Zaheer Sader, Vishek Inarman |  | EP 5 _ Invalid
3 | WBM3QA-1093 | INC6060807 | FML-5056 | FML-5250 | M3 | 20/10/2023 | 25/10/2023 | Ready for Prod | M3 Prod - Mandate lookup Table using Total Amount Excluding VAT instead of +VAT - CCN (EP5) | When the system validates a claim it uses the total amount excluding VAT instead of the amount +VAT. As seen below. The mandate is set at 15k, the claim is below the mandated amount excluding VAT and would not ask for a clearance request where as the amount is actually over 16k including VAT and a request for customer clearance should come up. After validating the claim is moves to “mandates are validated”. In the case of the supplier being NON VAT liable this would work fine with no issues. | When the system validates a specifc claim it should not use the total amount einclusive of VAT as per the customer mandate. System enhancement has been given as per EP. | Zaheer Sader, Vishek Inarman |  | All documents attached to the FML
4 | WBM3QA-1142 | INC5968987 | FML-4992 | FML-5250 | M3 | 20/10/2023 | 25/10/2023 | Ready for Prod | M3 - Prod - User overriding WAE assigned supplier (EP5) | The users are able to override the assigned WAE supplier as per attached example Risk: users are able to select their own suppliers and override the WAE which is against the agreements This will result in too many orders at one users, bay capacity override and unfair advantage to suppliers | Fix to not aallow agents to manually override the merchant selected by the WAE. This is to get better control on the allocation process. | Vishek Inarman, Zaheer Sader | All documents attached to the FML
5 | WBM3QA-1149 | INC6216728 | FML-5261 | FML-5250 | M3 | 11/10/2023 | 12/10/2023 | Ready for Prod | M3 Prod- Merchants- Soft block status functionality hard blocking payments and WO processing | Soft block status is intended to block a supplier from receiving any more new work while claims that have already been allocated to them prior to the soft block will not be blocked from processing any part in the claim including payments. Hard block is intended to put a stop to any and all processes, the supplier should not receive any new work and any open claims will be blocked from being processed. Currently the soft block function places a supplier on a hard block. | Soft block will now stop the merchant/supplier from getting more work via the WAE, but allow for already open work orders to be processed and paid. Soce change was introudced as per EP. | Vishek Inarman, Zaheer Sader | All documents attached to the FML
13 | WBM3QA-1193 | INC | FML- |  | M3 | 11/10/2025 | 12/10/2025 | No Longer Required - User Issue | M3 PROD - PRE INSPECTIONS ARE CREATING ADHOC INSPECTION TYPE | Pre inspections are being a created as adhoc inspection type which should not be the case. An adhoc should only be created if the inspector finds the vehicle on site without an initial request or inspection office team creates an adhoc for any special request / BOS. We need to investigate why the system is creating an adhoc’s even though there is a pre-inspection work order linked as per below screenshots. | This seems to be a user issue. Therefore solved as part of business process. | Senthan Nadasen | Senthan will update the ticket as it is a pass in Production.
16 | WBM3QA-1203 | INC | FML- |  | M3 | 11/10/2023 -PASSED | 12/10/2023 |  | M3 Prod - Automation on "invite to supplier" for accidents | As per our discussion today, after completing the pre inspection for an accident, we would like the system to automatically create the three damage assessment orders and have the status change to “email sent to inspector/supplier” since the invite will be sent automatically. although if we have an issue with sending out the invite to the supplier the damage assessment order should still be created but the status should show as “Draft”. | System now automatically create the three damage assessment orders and changes the status to “email sent to inspector/supplier” since the invite is sent automatically. Also, if there is an issue with sending out the invite to the supplier the damage assessment order should still be created but the status should show as “Draft” for it then to be sent out manually by the agent. This is changes to the logic and needed EP. | Vishek Inarman, Zaheer Sader
17 | WBM3QA-1209 | INC | FML- |  | M3 | 11/10/2023_PASSED | 12/10/2023 |  | Defaulting incorrect catalog part for vehicle part when no catalog part found | When there are no catalog parts found against the vehicle part, it should left blank. however, it looks like a random catalog part is being defaulted to the vehicle part. Add vehicle part and save. On calculate, brings up a random catalog part - INCORRECT. | ?? | Vishek Inarman, Zaheer Sader
18 | WBM3QA-1215 | INC6175384 | FML-5262 | FML-5250 | M3 | 11/10/2023 PASSED | 12/10/2023 | UAT Testing | Prod Miles - Generate and Send Statement Report to exclude RT46/SAPS customers |  | This is just to exclude the RT46 and SAPS customer form a specific bulk job. This is dont by making small changes to the selection. | Sharona Panday, Theresa Hughes
19 | SDWBSA-384 | INC | FML- |  | BAU | 11/10/2023 | 12/10/2023 |  | Miles Hanging - Sofico Service Desk - no XML required |  |  | Nkosinathi | Logged by Nkosinathi_This is not a BAU ticket , the ticket has been closed with the following comments: SQL logs for Miles prod were being requested for
20 | SDWBSA-412 | INC | FML- |  | BAU | 11/10/2023 | 12/10/2023 |  | Load report error-Direct debit |  |  | Sibusiso | Ticket was resolved on the system _ Logged by Sibu To be Re-tested
21 | SDWBSA-415 | INC5811819 | FML- 4668 |  | BAU | 11/10/2023 | 12/10/2023 |  | Interest rate change not reflected after customer invoicing jobs are executed - no XML required | Part of EP6 |  | Charmaine Odendaal | Logged by Sibu _ Ticket is in Resolved State
22 | SDWBSA-416 | INC | FML- |  | BAU | 11/10/2023 | 12/10/2023 |  | Early Payment discount | Awaiting Edith/Daniel's cofnfiration Related to Direct Credit changes |  | Daniel Maans, Chanel Saunders, Payments (Jane Booi, Edith Jacobs) | Sisanda to cofirm with Business if issue is resolved
23 | SDWBSA-2491 | INC6093863 | FML-5102 |  | BAU | 11/10/2023 | 12/10/2023 |  | NPS - incorrect Net Rental Compensation billing item | Nk to confirm |  | Himesh Laloo
24 | N/A | INC4798329 | FML-3773 |  | BAU | 11/10/2023 | 12/10/2023 |  | DIRECT DEBIT:Change of formula that populates debit order file | Passed |  | Deneshan Pillay | Test and passed. Test Results and user sign off added to Jira
25 | N/A | INC3675072 | FML-3027 |  | BAU | 11/10/2023 | 12/10/2023 |  | DIRECT DEBIT:Invoices after bill run are only consolidated in the following month | Passed |  | Deneshan Pillay | Test and passed. Test Results and user sign off added to Jira
26 | N/A | INC3675072 | FML-3634 |  | BAU | 11/10/2023 | 12/10/2023 |  | DIRECT DEBIT:Invoices after bill run are only consolidated in the following month | Passed |  | Deneshan Pillay | Test and passed. Test Results and user sign off added to Jira
| N/A |  | FML-4661 |  | BAU | 11/10/2023 | 12/10/2023 |  | TPSC:FNB Renewal for July not pulling on miles. | Passed |  | Awonke Mama | Tested / Passed test results Report added on Jira together with user sign off 09.10.23
| N/A | INC5771640 | FML-4615 |  | BAU | 11/10/2023 | 12/10/2023 |  | TPSC: Tracker Renewal orders | Passed |  | Edith Jacobs | Tested / Passed test results Report added on Jira together with user sign off 09.10.23
19 | N/A | INC5846873 | FML-4739 |  | BAU | 11/10/2023 | 12/10/2023 |  | DC: Payment File for 31/07/2023 failed | Still to be tested |  | Carmen Abdrabu
11 | N/A | INC5161027 | FML-4084 |  | BAU | 11/10/2023 | 12/10/2023 |  | TPSC: Units Not Pulling Into Renewal | Passed |  | Edith | Test and passed. Test Results and user sign off added to Jira
12 | N/A | INC5080431 | FML-3988 |  | BAU | 11/10/2023 | 12/10/2023 | Awaiting Prod sainty check | TPSC:Renewal order is pulling out duplicate vehicles registration. | Passed |  | Jane | Test and passed. Test Results and user sign off added to Jira
13 | N/A | INC4978013 | FML-3947 |  | BAU | 11/10/2023 | 12/10/2023 | Awaiting Prod sainty check | TPSC:Certrack: Miles Extract on LTC - Find Licensing details and validations from Certrack for all contracts - to include date and time stamp | Still to be tested |  | Edith/Jane | Nicolene
14 | N/A | INC4589948 | FML-3625 |  | BAU | 11/10/2023 | 12/10/2023 | Awaiting Prod sainty check | TPSC: Ctrack: Telematics Renewal Orders not generating for CTrack Fleet) | Passed |  | Edith/Jane | There is 2 parts to this test. I have tested with Edith and C TRACK is fine however I need to test with Jane - thanks Sandy

## 27 October Deployment
FML-5365 - Wintel - Miles Prod Snapshot FML-5366 - DBA - EP7 Miles Prod deployment. FML-5367 - Weblogic - Miles Prod EP7 Deployment. FML-5368 - Weblogic - Miles Prod EP7 XML Deployment. FML-5397 - DBA - Miles Scripts Deployment.
# | Sofico Jira # | ServiceNow # | FML # | DI # | Stream | QA Sign off Date | UAT Sign off Date | Status | Description | Issue Description | Resolution | Business User | Assignee (Config Resource) | UAT test results | Tested in Prod | Comments | INC number
1 | WBM3QA-1033 | INC6060778 | FML-5058 | FML-5368 | M3 | 20/10/2023 | 25/10/2023 | Deployed to Production | Benchmark pricing to pull per make and model - PostGoLive CCN (EP5) | Benchmark pricing to be fixed by per make and model currently it is pulling by make showing multiple models parts when looking for a specific benchmarked price. Baskets to be linked to the GVM codes. | When entering the quote and specific line items, when hitting calculate the specific benchmarked price will be populated by per make and model | Zaheer Sader, Vishek Inarman, Jadyn Marzuoli, Travis Padachy, Warren Naidoo |  | Zaheer- Tested and Passed | to request approval
2 | WBM3QA-1062 | INC6060785 | FML-5401 | FML-5367 | M3 | 20/10/2023 | 25/10/2023 | Deployed to Production | M3 Prod - System is not removing the existing Merchant after disapproving the Order (EP5) | This is for Work Orders: *Create WO for specific FV, with specific Milage. *Once approved, I disapproved, and close the specific WO. *from the SAME FV, a new WO is created, with the same Mileage. *The exact same merchant which disapproved in the previous WO gets allocated again. | Functionailty to recognise the disppaorved merchant, and not when trying to reallocate to a different merchant the same merchant isnt picked up. WAE refinement | Zaheer Sader, Vishek Inarman |  | Zaheer- Tested and Passed | Zaheer- Tested and Failed | the same supplier is populating on the new work order as the previous disapproved one | INC6335377
3 | WBM3QA-1093 | INC6060807 | FML-5056 | FML-5397 FML-5368 | M3 | 20/10/2023 | 25/10/2023 | Deployed to Production | M3 Prod - Mandate lookup Table using Total Amount Excluding VAT instead of +VAT - CCN (EP5) | When the system validates a claim it uses the total amount excluding VAT instead of the amount +VAT. As seen below. The mandate is set at 15k, the claim is below the mandated amount excluding VAT and would not ask for a clearance request where as the amount is actually over 16k including VAT and a request for customer clearance should come up. After validating the claim is moves to “mandates are validated”. In the case of the supplier being NON VAT liable this would work fine with no issues. | When the system validates a specifc claim it should not use the total amount einclusive of VAT as per the customer mandate. System enhancement has been given as per EP. | Zaheer Sader, Vishek Inarman |  | Zaheer- Tested and Passed | Zaheer- Tested and Passed | hard block when validating the claim. Seems to be related to mandate fix | INC6335368
4 | WBM3QA-1142 | INC5968987 | FML-4992 | FML-5367 | M3 | 20/10/2023 | 25/10/2023 | Deployed to Production | M3 - Prod - User overriding WAE assigned supplier (EP5) | The users are able to override the assigned WAE supplier as per attached example Risk: users are able to select their own suppliers and override the WAE which is against the agreements This will result in too many orders at one users, bay capacity override and unfair advantage to suppliers | Fix to not aallow agents to manually override the merchant selected by the WAE. This is to get better control on the allocation process. | Vishek Inarman, Zaheer Sader |  | Zaheer- Tested and Passed | Zaheer- Tested and Passed
5 | WBM3QA-1149 | INC6216728 | FML-5261 | FML-5367 | M3 | 20/10/2023 | 25/10/2023 | Deployed to Production | M3 Prod- Merchants- Soft block status functionality hard blocking payments and WO processing | Soft block status is intended to block a supplier from receiving any more new work while claims that have already been allocated to them prior to the soft block will not be blocked from processing any part in the claim including payments. Hard block is intended to put a stop to any and all processes, the supplier should not receive any new work and any open claims will be blocked from being processed. Currently the soft block function places a supplier on a hard block. | Soft block will now stop the merchant/supplier from getting more work via the WAE, but allow for already open work orders to be processed and paid. Soce change was introudced as per EP. | Vishek Inarman, Chanel Saunders |  | Awaiting UAT Testing Results. | buffering solution..
6 | WBM3QA-1203 | INC6301302 | FML-5385 | FML-5368 | M3 | 20/10/2023 | 25/10/2023 | Deployed to Production | M3 Prod - Automation on "invite to supplier" for accidents (EP6) | As per our discussion today, after completing the pre inspection for an accident, we would like the system to automatically create the three damage assessment orders and have the status change to “email sent to inspector/supplier” since the invite will be sent automatically. although if we have an issue with sending out the invite to the supplier the damage assessment order should still be created but the status should show as “Draft”. please let me know if more clarity is needed. |  | Vishek Inarman, Zaheer Sader |  | Zaheer- Tested and Passed | Zaheer- Tested and Passed
7 | WBM3QA-1209 WBSA-2494 | INC6301241 | FML-5386 | FML-5367 | M3 | 20/10/2023 | 25/10/2023 | Deployed to Production | Defaulting incorrect catalog part for vehicle part when no catalog part found (EP6) | When there are no catalog parts found against the vehicle part, it should left blank. however, it looks like a random catalog part is being defaulted to the vehicle part. Add vehicle part and save. On calculate, brings up a random catalog part - INCORRECT. |  | Vishek Inarman, Zaheer Sader |  | Zaheer- Tested and Passed | Zaheer- Tested and Passed
8 | WBM3QA-1226 | INC6316916 | FML-5398 | FML-5368 | M3 | 20/10/2023 | 25/10/2023 | Deployed to Production | Recharge Amount is not being updated when Part Price is changed. | After resetting a WO and updating the Part Price, when you recalculate and validate the Recharge Amount is not being updated. |  | Vishek Inarman, Zaheer Sader |  | Zaheer- Tested and Passed | Zaheer- Tested and Passed
9 | WBM3QA-1229 | INC6316924 | FML-5399 | FML-5367 | M3 | 20/10/2023 | 25/10/2023 | Deployed to Production | WO status not changing after sending approval documents to Supplier | Wo status is not changing to Authorisation sent to merchant after sending the approval documents to supplier. Approval to supplier was send successfully. |  | Vishek Inarman, Zaheer Sader |  | Zaheer- Tested and Passed | Zaheer- Tested and Passed
10 | WBSA-2491 | INC6093863 | FML-5102 | FML-5367 | BAU | 20/10/2023 | 25/10/2023 | Deployed to Production | NPS - incorrect Net Rental Compensation billing item | Please see attached list of 103 Shoprite deals for which I am unable to activate restructures. The amort tables are not calculating properly and as a result, the ending capital is not equating to the RV, causing the rental to miscalculate. We need to correct these the same way we did back in May this year. Note that I still await Shoprite's approval for the restructure but once approved, we only have until tomorrow to correct these. I have loaded and saved all of the AQs in PROD. Kindly perform a DB refresh in the environment we are going to test in. The contract IDs are provided in column BF of the attached spreadsheet and the AQ numbers are in column BH. The correct rental to match is in column AB and the deviation on the AQ resulting from the amort miscalculation in PROD is in column BO. |  | Himesh Laloo, Deneshan Pillay |  | Meeting with Pran, Himesh and Denashin during the 08:00-09:00 meeting |  | To be tested post Bill runs this week
11 | SDWBSA-384 | INC6301465 | FML-5383 | FML-5367 | BAU | 20/10/2023 | 25/10/2023 | Deployed to Production | Miles Hanging - Sofico Service Desk |  |  |  |  | Sandy: tested with the users - Test Results added to Jira. Attached user sign off - 24.10.23 | Daniel - Tested and Passed
12 | SDWBSA-412 | INC | FML-5419 | FML- | BAU | 20/10/2023 | 25/10/2023 | Deployed to Production | Miles Direct Debit Load Report Import error - Sofico Service Desk |  |  | Charmaine Odendaal |  | To be tested today 24.10.2023 Feedback from QA, awaiting Fintegrate file (Lindiwe) This is specifically on the error message. Lindi to do run this morning 26.10.2023 (to provide feedback) |  | To be tested on Wednesday
13 | SDWBSA-415 | INC5811819 | FML-4668 | FML-5367 | BAU | 20/10/2023 | 25/10/2023 | Deployed to Production | Interest rate change not reflected after customer invoicing jobs are executed |  |  | Charmaine Odendaal |  | This ticket was tested and test results attached to Jira. |  | To be tested post Bill runs this week
14 | SDWBSA-416 | INC6302108 | FML-5384 | FML-5367 | BAU | 20/10/2023 | 25/10/2023 | Deployed to Production | Calculate early payment discounts - Sofico Service Desk |  |  | Edith Jacobs, Daniel Maans |  | Sandy: tested with the users - ticket passed. Test Results and User sign off attached on Jira |  | To be tested post Bill runs this week

## 10 November 2023
# | Sofico Jira # | ServiceNow # | FML # | DI# | Stream | QA Sign off Date | UAT Sign off Date | Status | Description | Issue Description | Resolution | Business User | Assignee (QA+Config Resource) | Comments
1 | WBM3QA-950 | INC5870495 | FML- | FML- | M3 | 06/11/2023 | 08/11/2023 | UAT in Progress | Prod M3 - Internal fleet list overnight | Missing columns on internal fleet list BI ID: 650129 Columns G – Contract No Columns T – Driver Name Columns BP – Net Book Value Columns BW – Maintenance Income Columns BX – Maintenance Expense Columns BY – Maintenance Chargeback Columns BZ – Tyre Income Columns CA – Tyre Expense Columns CB – Tyre Chargeback Columns CC – License Renewal Income Columns CD – License Renewal Expense Columns CE – License Renewal Chargeback |  | Himes Laloo | N/A | Check with Pieter. Linked to 1180. Pieter and Jan to resolve it in a meeting on 06 Nov.
2 | WBM3QA-960 | INC6317394 | FML-5400 | FML- | M3 | 06/11/2023 | 08/11/2023 | UAT in Progress | Main repair order addition | Please can you enable the main repair order on the incident /accident screen. This will allow corporate to use the accident limits for users/mandates within the system Required for RT46 go live not for code go live for this coming weekend |  | Travis Padachy, Warren Naidoo | Nokuthula
3 | WBM3QA-1181 | INC | FML- | FML- | M3 | 06/11/2023 | 08/11/2023 | QA in Progress | Authorisation Number to trace the transaction from end to end. | Autocard is looking for an Authorisation Number from Miles that will be the same from Pre-Authorisation Number to Authorisation Number for end-to-end traceability. |  | Zaheer Sader, Vishek Inarman, Travis Padachy, Warren Naidoo | WO/TO-Abel Noks-AO
4 | WBM3QA-1192 | INC | FML- | FML- | M3 | 06/11/2023 | 08/11/2023 | UAT in Progress | Set Invoice Type on Sales Invoice to read only (XML for SDWBSA-383) |  |  | Nealan Michaels | N/A | Sent to Nealan for UAT.
5 | WBM3QA-1196 | INC | FML- | FML- | M3 | 06/11/2023 | 08/11/2023 | QA in Progress | Out of Fleet and Terminated Contracts -> Change to Active | During migration, fleetvehicles and contracts were migrated as Out of Fleet and Terminated when the the card status indicated it was not active. The issue is that AutoCard will indicate the card status as cancelled, but the Manage Maintenance component was still active. Business now need to use the fleet vehicle and contract, but are unable to do so. |  | Theresa Hughes , Thuso Nwedamutswu, Zaheer Sader | Lindiwe | To be tested on 06 Nov in a meeting with Pieter and everyone inveolved.
6 | WBM3QA-1199 | INC | FML- | FML- | M3 | 06/11/2023 | 08/11/2023 | UAT in Progress | M3 PROD - DRAFT STATUS TO BE CANCELLED IF INSPECTION NOT REQUIRED | Please can you assist to get all draft assessment orders removed from the system if the inspection is not required. |  | Senthan.Nadasen, Peter Zacheus | N/A
7 | WBM3QA-1218 | INC6356680 | FML-5448 | FML- | M3 | 06/11/2023 | 08/11/2023 | UAT in Progress | M3 Prod - Recharge amount Sometimes not Populating | The recharge amount was not auto populating when validating the claim. Please not this is not the case all the time but it does happen daily. |  |  | Nokuthula
8 | [WBM3QA-1228 | INC | FML- | FML- | M3 | 2023-06-11 | 2023-08-11 | UAT in Progress | Validation on input values on supplier profile - black ownership percentage - Alpha instead of Numeric |  |  |  | Jongi
9 | WBM3QA-1230 | INC | FML- | FML- | M3 | 06/11/2023 | 08/11/2023 | UAT in Progress | Car Wash - Work Order Import Connector |  |  |  | Lindi
10 |  |  | FML-3027 |  | BAU | Passed UAT and QA | Passed UAT | Ready for Prod | DD:Invoices after bill run are only consolidated in the following month | REFER TO FML-3027 FOR XML AND DATABASE SCRIPT AND READ DEPLOYMENT INSTRUCTIONS CAREFULLY Debit order customers- Invoices generated after bill run till end of the month before debit order submission are being included in the debit order and not appearing on a customers invoices until the following month. EFT Customers the same applies and customers see it on their statement but have to wait for the next consolidated invoice job run to generate the document. On Implementation Create Selection on Config (Find customer with outstanding payables for direct debit2) on Dev Import Selection on Prod Copy BO xml to connectors folder Add selection ID to BO (Selection For Payables To Invoice) Debit Order File must look for recharge invoices that are consolidated. In this case the customer has not received the Invoices but has been debited - DENESHAN PILLAY - 05.10.23 |  | Deneshan Pillay | Sandy | Tested on QA and Passed. Tesults results and User sign off on attached to Jira
11 |  |  | FML-3625 |  | BAU |  |  | Development | TPSC: Crack: Telematics Renewal Orders not generating for CTrack Fleet) |  |  | Edith Jacobs | Sandy | Additional QA assistance required
12 |  |  | FML-3634 |  | BAU | Passed QA | Passed UAT | Ready for Prod | DD:BP customer debited multiple times for same invoice |  |  | Deneshan Pillay | Sandy | Tested and passed in QA- UAT sign off in order
13 |  |  | FML-3773 |  | BAU | Passed QA | Passed UAT | Ready for Prod | DD:Change of formula that populates debit order file |  |  | Deneshan Pillay | Sandy | Tested on QA passed 03.11.23
14 |  |  | FML-3845 |  | BAU | Not QA tested | No UAT evidence but Sign-Off email prodivded | UAT in Progress | CR:The client Fantique Trade 869 (Pty)Ltd, the system have allowed the ordering of vehicles to exceed Group Credit limit of R1 218 382 by R929 120, resulting in the exposure being R2 147 50. |  |  | Isabel Maduane / Maletsatsi Muchinya | Zenzele | Additional QA assistance required / Business tested and passed 2.11.23. Zenzele to check with Sandy if QA feedback is already there
15 |  |  | FML-4375 |  |  | Not QA tested | No UAT evidence but Sign-Off email prodivded | UAT in Progress | INTERIM FIX:Miles facility screen reflects negative credit available and credit overview/ existing limit is more than what was previously approved on CRO. |  |  | Maletsatsi Muchinya | Zenzele | Business tested and Passed 2.11.23. Zenzele to check with Sandy if QA feedback is already there
16 |  |  | FML-4732 |  | BAU | Not QA tested | No UAT evidence but Sign-Off email prodivded | UAT in Progress | CR:Incorrect Credit Risk amount - current exposure |  |  | Maletsatsi Muchinya | Sandy | Additional QA assistance required / Business tested and passed 2.11.23
17 |  |  | FML-5390 |  | BAU | Not QA tested | No UAT evidence but Sign-Off email prodivded | UAT in Progress | Miles facility screen reflects negative credit available and credit overview/ existing limit is more than what was previously approved on CRO. |  |  | Maletsatsi Muchinya | Sandy | Business tested and Passed 2.11.23.
18 |  |  | FML-3947 |  | BAU |  |  | QA in Progress | TPSC:Certrack: Miles Extract on LTC - Find Licensing details and validations from Certrack for all contracts - to include date and time stamp |  |  | Nicolene Potgieter | Sandy
19 |  |  | FML-3988 |  | BAU |  |  | Development | TPSC:Renewal order is pulling out duplicate vehicles registration. | TPSC:Renewal order is pulling out duplicate vehicles registration. |  | Edith Jacobs / Jane Booi | Sandy | Ravi / Mandla busy fixing this. XML files need to be imported again to QA and UAT 1.11.2023
20 |  |  | FML-4313 |  | BAU |  |  | QA in Progress | SI:1 (May FML Ops Manco). Prime Interest Rate Not Updating on Certain Deals, Refer to the attached analysis, there are an estimated 163 deals on which the Prime Interest Rate has not updated to the latest Prime rate as at 2023-05-09. This needs to be resolved urgently please. Contact me if you need any help. Info: setup as variable interest rate they are still sitting with the old interest |  |  | Himesh Laloo
21 |  |  | FML-4424 |  | BAU |  |  | QA in Progress | Vehicle disposal losses - the system does not block a settlement that is done at less than book value. |  |  | Nicolene Potgieter /Themba Moyo | Sandy
22 |  |  | FML-4538 |  | BAU |  |  | QA in Progress | Certrack upload file - if there are multiple deal numbers then the vehicles do not update with the certrack information ie. OPL plus Mm deal The system must allow for both the MM and OPL deal to be updated with certrack information. Attached is a copy of the error report for these. It is important for this to be done as the number of deals with two contracts are increasing. |  |  | Nicolene Potgieter Mandla | Sandy
23 |  |  | FML-4574 |  | BAU |  |  | QA in Progress | JASPER:Require the ability to generate an Early Settlement letter with all the correct values | Problem Statement/Opportunity When initiating a fleet vehicle leasing contract, the total revenue that will be recovered at the end of the contract is pre calculated. This amount must be recovered regardless of whether there is an early settlement by the customer or not. The current issue experienced is that where a customer/client requests for their vehicle contract to be terminated earlier (e.g., 3/6 months or more) a settlement quote must be sent to them for acceptance. However, it has been raised by customers that subsequent to paying the settlement amount as quoted on the settlement letter, they still receive statements from WB stipulating that they still have outstanding charges, these could either be future billings or previous rentals not paid. There was no consistent application of what should be included in the settlement value provided to the customer and the system settlement letter was often adjusted to include arrear rentals. This causes issues for both the client and business since there are numerous complaints which are received from clients stating that they have been provided with an amount that they have subsequently paid however they are still being charged for other amounts over and above what has been paid. Future arrears will still be settled, and the customer is liable to pay for them. The solution for the stipulated business problem is that going forward when a client requests for an early settlement for their vehicle contract, the settlement letter must include all of the future billings which can be calculated using the initial contract agreement amount. The settlement letter will not include arrear rentals and the system generated settlement letter will be used. |  | Mapeka Shomang | Sandy | Tested on QA and Passed. Tesults results and User sign off on attached to Jira BUT MAYA wants Themba to make changes 31.10.23
24 |  |  | FML-4615 |  | BAU |  |  | Development | TPSC: Tracker Renewal orders |  |  | Edith Jacobs | Sandy | Additional QA assistance required
25 |  |  | FML-4661 |  | BAU |  |  | Development | TPSC:FNB Renewal for July not pulling on miles. |  |  | Edith Jacobs | Sandy
26 |  |  | FML-4693 |  | BAU | Passed QA |  | UAT in Progress | JASPER:Debtor statement not consolidating amount by Invoice doc |  |  | Deneshan Pillay | Sandy | Nandi reapplied the changes on QA and UAT. Cud not find the amount on the Jasper report. Deneshan will have to look in prod.
27 |  |  | FML-4736 |  | BAU | Passed QA |  | UAT in Progress | JASPER: remittance showing duplicate order numbers when paying multiple orders on one purchase invoice |  |  | Jane Booi | Sandy | Sandy to speak to Jane and Edith. Jane on leave.
28 |  |  | FML-4739 |  | BAU |  |  | QA in Progress | CR:The client Fantique Trade 869 (Pty)Ltd, the system have allowed the ordering of vehicles to exceed Group Credit limit of R1 218 382 by R929 120, resulting in the exposure being R2 147 50. |  |  | Isabel Maduane | Zenzele
29 |  |  | FML-4968 |  | BAU | Passed QA |  | UAT in Progress | Add in filter option for Bank EFT allocations to include Consolidated Invoice reference |  |  | Deneshan Pillay | Sandy
30 |  |  | FML-5010 |  | BAU | Passed QA | Passed UAT | Ready for Prod | Unable to open work order on vehicle - CY289048 |  |  | Travis Padachy | Sandy | Tested passed User sign off and test Results on Jira
31 |  |  | FML-5013 |  | BAU |  |  | QA in Progress | ACB file has all the fields populated but the cost centre issues is preventing payments. Config to investigate |  |  | Daniel Maans | Zenzele
32 |  |  | FML-5240 |  | BAU |  |  | QA in Progress | DBR Job Seats (Miles) |  |  | Johannes Wilters |  | BA to check with Sisanda who to talk to for this ticket
33 |  |  | FML-5306 |  | BAU | Passed QA | Passed UAT | Ready for Prod | A deal for Stowe was terminated on the system before it was returned as it was at the dealer to be fixed. Now we need to reactivate so OPS can terminate on Mil |  |  | Goodman Nkosi
34 |  |  | FML-5341 |  | BAU | Passed QA | UAT screenshots needed but sign-Off is provided | Ready for Prod | CR FInance - Request for Display of history attribute | We need an audit trail for payments and need to identify who made changes to any payment transaction or file. Refer to Settlement discount query where the due date was changed after a payment file rejected and we could not pick up who/why the due date was changed to almost 60 days Currently history attributes have not been activated and is required to have a full audit trail |  | Edith Jacobs | Sandy | QA test evidence is there but no UAT test evidence. Sign-off is provided.
35 |  |  | FML-5342 |  | BAU |  |  | QA in Progress | DC FIN - ACB failure of R26 million in payments due to Primary role being removed. Miles doesn`t log certain critically important actions on the supplier screen. |  |  | Daniel Maans | Sandy
36 |  |  | FML-5379 |  | BAU | Failed QA | Development | QA in Progress | Please review release and term and reloads quotation process Procurement is having system issues when trying to activate sales and leaseback\ release and term and reload deals. |  |  | Dalita Tshabalala |  | This fix is not in QA / UAT. Dalita and I tested this 06.11.2023 - Dalita stressed that its important for this change to go in as it affects the NET PRICE on the Contract.
37 |  |  | FML-5422 |  | BAU |  |  | QA in Progress | Shoprite Checkers Miles Cost Centres Duplicated |  |  | Klyne Poliah | Sandy | BA to talk to the user and get more desription
38 |  | INC5228951 | FML-5454 /FML-5248 |  | BAU | Passed QA | UAT screenshots needed but sign-Off is provided | Ready for Prod | CLONE - INC5228951 to update book values was taken to prod yesterday. Please see vehicles that did not update | INC5228951 to update book values was taken to prod yesterday. Please see vehicles that did not update. |  | Nicolene Potgieter | Sandy | QA test evidence is there but no UAT test evidence. Sign-off is provided.

## Sheet1
7 | WBM3QA-1210 | INC | FML- | FML- | M3 | 06/11/2023 | 08/11/2023 | Sofico+DM investigating further | M3 Prod - Incorrect contract pulling through on MRO | Quotation has been loaded, try to send out the clearance but unable to send it. | Aidan Alexander, Zaheer Sader, Vishek Inarman | Nokuthula | Check with Pieter. Linked to 1180. Pieter and Jan to resolve it in a meeting on 06 Nov.

## 2 Weekly tickets
# | Sofico Jira # | ServiceNow # | FML # | DI# | Stream | QA Sign off Date | UAT Sign off Date | Status | Description | Issue Description | Resolution | Business User | Assignee (Config Resource) | Comments
1 | [WBM3QA-1134] | INC | FML- | FML- | M3 | 06/11/2023 | 08/11/2023 |  | Post billing selection checks | As discussed last week kindly provide post billing selections
2 | WBM3QA-1165 | INC | FML- | FML- | M3 | 06/11/2023 | 08/11/2023 |  | M3 Prod - Incorrect message on WO if email not set (Dev fix) | Root cause: The mandated RMT User email address not loaded hence not sending clearance automatically When agent is performing a WO and the email of the RMT Mandated Official (RMT User) is not set then the automatic clearance is not sent out. The status on the work order does not update to Clearance required user must via workflow change status to clearance required then email out the clearance doc However the error message received does not state the issue of the email but states that the mandates are set to zero.
3 | WBM3QA-1184 | INC | FML- | FML- | M3 | 06/11/2023 | 08/11/2023 |  | M3 Go Live - Autocard cancellation doesnt equal MM Contract Term in Miles | Users get the autocard report and terminate all MM contracts when a card has been cancelled - reported lost / stolen - and then want to activate when the card has been re-issued. Users MUST NOT cancel the MM contract on Miles as this only speaks to the fuel transaction side and has no bearing on the Managed maintenance contract on Miles. Miles MM contracts should only be terminated when the actual asset is sold/stolen/ or removed from the fleet.
4 | WBM3QA-1205 | INC | FML- | FML- | M3 | 06/11/2023 | 08/11/2023 |  | M3 Prod - RMT Error from Payments (DEV fix) | When the system validates a claim it uses the total amount excluding VAT instead of the amount +VAT. As seen below. The mandate is set at 15k, the claim is below the mandated amount excluding VAT and would not ask for a clearance request where as the amount is actually over 16k including VAT and a request for customer clearance should come up. After validating the claim is moves to “mandates are validated”. In the case of the supplier being NON VAT liable this would work fine with no issues.
| WBM3QA-1208 | INC | FML- | FML- | M3 | 06/11/2023 | 08/11/2023 |  | Confirmed work orders not reverting back to waiting for approval on changes and not resolving contract and customer ids (Dev fix)