## 10 November 2023
FML-5473, FML-5474, DBA DI = FML-5475,
# | Sofico Jira # | ServiceNow # | FML # | DI# | Stream | QA Sign off Date | UAT Sign off Date | Status | Description | Issue Description | Resolution | Business User | Department | Assignee (QA+Config Resource) | Comments
1 | WBM3QA-950 | INC5870495/ INC5957920 | FML-4945 | FML-5474 | M3 | 06/11/2023 | 08/11/2023 | Ready for Prod | Prod M3 - Internal fleet list overnight | Missing columns on internal fleet list BI ID: 650129 Columns G – Contract No Columns T – Driver Name Columns BP – Net Book Value Columns BW – Maintenance Income Columns BX – Maintenance Expense Columns BY – Maintenance Chargeback Columns BZ – Tyre Income Columns CA – Tyre Expense Columns CB – Tyre Chargeback Columns CC – License Renewal Income Columns CD – License Renewal Expense Columns CE – License Renewal Chargeback |  | Himes Laloo | Risk & Pricing | Nkosinathi
2 | WBM3QA-960 | INC6317394 | FML-5400 | FML-5473 | M3 | 06/11/2023 | 08/11/2023 | Ready for Prod | Main repair order addition | Please can you enable the main repair order on the incident /accident screen. This will allow corporate to use the accident limits for users/mandates within the system Required for RT46 go live not for code go live for this coming weekend |  | Travis Padachy, Warren Naidoo | CC - Corp | Nokuthula
3 | WBM3QA-1199 | INC6393451 | FML-5479 | FML-5473 | M3 | 06/11/2023 | 08/11/2023 | Ready for Prod | M3 PROD - DRAFT STATUS TO BE CANCELLED IF INSPECTION NOT REQUIRED | Please can you assist to get all draft assessment orders removed from the system if the inspection is not required. |  | Senthan Nadasen, Peter Zacheus | Inspection | Zenzele/ Nkosinathi
4 | WBM3QA-1218 | INC6356680 | FML-5448 | FML-5473 | M3 | 06/11/2023 | 08/11/2023 | Ready for Prod | M3 Prod - Recharge amount Sometimes not Populating | The recharge amount was not auto populating when validating the claim. Please not this is not the case all the time but it does happen daily. |  | Zaheer Sader, Vishek Inarman, Travis Padachy, Warren Naidoo | CC - RT46 | Nokuthula
5 | [WBM3QA-1228 | INC6400496 | FML-5485 | FML-5473 | M3 | 2023-06-11 | 2023-08-11 | Ready for Prod | Validation on input values on supplier profile - black ownership percentage - Alpha instead of Numeric |  |  | Chanel Saunders | Merchant - RT46 | Jongi
6 | WBM3QA-1230 | INC6400502 | FML-5486 | FML-5473 | M3 | 06/11/2023 | 2023-08-11 | Ready for Prod | Car Wash - Work Order Import Connector |  |  | Zaheer, Nicole, Lindo and Amanda | CC - RT46 | Lindi
7 | WBM3QA-1233 | INC6398181 | FML-5487 | FML-5474 | M3 | 08/11/2023 | 08/11/2023 | Ready for Prod | Now that benchmark pricing is populating with EP7 - the % Variance is populating wrong on the clearance |  |  | Zaheer Sader, Vishek Inarman | CC - RT46 | Lindi
8 |  |  | FML-3027 | FML-5473 | BAU | Passed QA | Passed UAT | Ready for Prod | DD -Invoices after bill run are only consolidated in the following month | REFER TO FML-3027 FOR XML AND DATABASE SCRIPT AND READ DEPLOYMENT INSTRUCTIONS CAREFULLY Debit order customers- Invoices generated after bill run till end of the month before debit order submission are being included in the debit order and not appearing on a customers invoices until the following month. EFT Customers the same applies and customers see it on their statement but have to wait for the next consolidated invoice job run to generate the document. On Implementation Create Selection on Config (Find customer with outstanding payables for direct debit2) on Dev Import Selection on Prod Copy BO xml to connectors folder Add selection ID to BO (Selection For Payables To Invoice) Debit Order File must look for recharge invoices that are consolidated. In this case the customer has not received the Invoices but has been debited - DENESHAN PILLAY - 05.10.23 |  | Deneshan Pillay | Finance - Accounts Receivable | Sandy
9 |  |  | FML-3634 | FML-5473 | BAU | Passed QA | Passed UAT | Ready for Prod | DD-BP Customer debited multiple times for same invoice |  |  | Deneshan Pillay | Finance - Accounts Receivable | Sandy
10 |  |  | FML-3773 | FML-5473 | BAU | Passed QA | Passed UAT | Ready for Prod | DD-Change of formula that populates debit order file |  |  | Deneshan Pillay | Finance - Accounts Receivable | Sandy
11 |  |  | FML-4375 | FML-5473/ FML-5474 | BAU | No QA required | Passed UAT | Ready for Prod | INTERIM FIX:Miles facility screen reflects negative credit available and credit overview/ existing limit is more than what was previously approved on CRO. |  |  | Maletsatsi Muchinya | Finance - Credit | Zenzele
12 |  |  | FML-4732 | FML-5473/ FML-5474 | BAU | No QA required | Passed UAT | Ready for Prod | CR-Incorrect Credit Risk amount - current exposure |  |  | Maletsatsi Muchinya | Finance - Credit | Sandy
13 |  |  | FML-5390 | FML-5473/ FML-5474 | BAU | No QA required | Passed UAT | Ready for Prod | Miles facility screen reflects negative credit available and credit overview existing limit is more than what was previously approved on CRO. |  |  | Maletsatsi Muchinya | Finance - Credit | Sandy
14 |  |  | FML-3845 | FML-5473/ FML-5474 | BAU | Passed QA | Passed UAT | Ready for Prod | CR:The client Fantique Trade 869 (Pty)Ltd, the system have allowed the ordering of vehicles to exceed Group Credit limit of R1 218 382 by R929 120, resulting in the exposure being R2 147 50. |  |  | Isabel Maduane / Maletsatsi Muchinya | Finance - Credit | Zenzele
15 |  |  | FML-3625 | FML-5473/ FML-5475 | BAU | Passed QA | Passed UAT | Ready for Prod | TPSC-Crack Telematics Renewal Orders not generating for CTrack Fleet |  |  | Edith Jacobs | Finance - Accounts Payable | Sandy
16 |  |  | FML-3988 | FML-5473/ FML-5475 | BAU | Passed QA | Passed UAT | Ready for Prod | TPSC -Renewal order is pulling out duplicate vehicles registration | TPSC:Renewal order is pulling out duplicate vehicles registration. |  | Edith Jacobs / Jane Booi | Finance - Accounts Payable | Sandy
17 |  |  | FML-4464 | FML-5473/ FML-5475 | BAU | Passed QA | Passed UAT | Ready for Prod | TPSC-Renewal incomplete |  |  | Edith Jacobs | Finance - Accounts Payable | Sandy
18 |  |  | FML-4615 | FML-5473/ FML-5475 | BAU |  | Passed UAT | Ready for Prod | TPSC-Tracker Renewal orders |  |  | Edith Jacobs | Finance - Accounts Payable | Sandy
19 |  | INC6332565 | FML-5431 | FML-5473/ FML-5475 | BAU | Passed QA | Passed UAT | Ready for Prod | TPSC Create the necessary database scripts to update the Service provider to WEBFLEET for the 52 contracts under the customer Stowe Holdingsed earlier. the telematics is under Webfleet but on the TPSC the provider is showing Tracker which is incorrect and resulting in the renewal order not to run under Webfleet. |  |  | Daniel Maans | Procurement | Sandy
20 |  |  | FML-4538 | FML-5473 | BAU | Passed QA | Passed UAT | Ready for Prod | Certrack upload file - if there are multiple deal numbers then the vehicles do not update with the certrack information ie. OPL plus MM deal The system must allow for both the MM and OPL deal to be updated with certrack information. Attached is a copy of the error report for these. It is important for this to be done as the number of deals with two contracts are increasing. |  |  | Nicolene Potgieter | Sales - Remarketing | Lindiwe
21 |  |  | FML-4693 | FML-5474 | BAU | Passed QA | Passed UAT | Ready for Prod | JASPER:Debtor statement not consolidating amount by Invoice doc |  |  | Deneshan Pillay | Finance - Accounts Receivable | Sandy
22 |  |  | FML-4739 | FML-5473/ FML-5474 | BAU | Passed QA | Passed UAT | Ready for Prod | DC Payment File for 31-07-2023 failed |  |  | Daniel Maans | Procurement | Sandy
23 |  |  | FML-5013 | FML-5473/ FML-5474 | BAU | Passed QA | Passed UAT | Ready for Prod | ACB file has all the fields populated but the cost centre issues is preventing payments. Config to investigate |  |  | Daniel Maans | Procurement | Zenzele
24 |  |  | FML-4968 | FML-5473 | BAU | Passed QA | Passed UAT | Ready for Prod | Add in filter option for Bank EFT allocations to include Consolidated Invoice reference |  |  | Deneshan Pillay | Finance - Accounts Receivable | Zenzele
25 |  |  | FML-5010 | FML-5475 | BAU | Passed QA | Passed UAT | Ready for Prod | Unable to open work order on vehicle - CY289048 |  |  | Travis Padachy | CC - Corp | Sandy
26 |  |  | FML-5240 | FML-5473 | BAU | Not Required | Passed UAT | Ready for Prod | DBR Job Seats (Miles) |  |  | Carmeroon Clark | Retail Rentals | Zenzele Nkosinathi
27 |  |  | FML-5306 | FML-5475 | BAU | Passed QA | Passed UAT | Ready for Prod | A deal for Stowe was terminated on the system before it was returned as it was at the dealer to be fixed. Now we need to reactivate so OPS can terminate on Mil |  |  | Goodman Nkosi | Sales - Remarketing | Sandy
28 |  |  | FML-5341 | FML-5473 | BAU | Passed QA | Passed UAT | Ready for Prod | CR FInance - Request for Display of history Attribute | We need an audit trail for payments and need to identify who made changes to any payment transaction or file. Refer to Settlement discount query where the due date was changed after a payment file rejected and we could not pick up who/why the due date was changed to almost 60 days Currently history attributes have not been activated and is required to have a full audit trail |  | Edith Jacobs | Finance | Sandy
29 |  | INC5228951 | FML-5454 /FML-5248 | FML-5473 | BAU | Passed QA | Passed UAT | Ready for Prod | CLONE - INC5228951 to update book values was taken to prod yesterday. Please see vehicles that did not update | INC5228951 to update book values was taken to prod yesterday. Please see vehicles that did not update. |  | Nicolene Potgieter | Sales - Remarketing | Sandy
30 |  | INC6327290 | FML-5417 | FML-5475 | BAU | Not Required | Not Required | Ready for Prod | Miles Password Rule |  |  | N/A | N/A | Nkosinathi
31 |  |  | FML-3624 | FML-5477 / FML-5476 | BAU | Passed QA | Passed UAT | Ready for Prod | Automation of Certrack file | Currently the upload of contract details are manually uploaded into certrack to extract the asset data from the eNatis system. The Certrack file runs overnight as there are approximately 18 000 vin numbers that are uploaded.The file is then extracted from Certrack to be uploaded by IT into the Miles system. The data is then analysed by using the extract in the Long Term Contracts modue called Certack Validation. The main purpose of this upload is to check for licence renewal dates and asset status (de-registered, police clearance required) Business is looking for automation of this process as it is very time consuming to upload the files and then to analyse the data. Business Risk The risk is that contract licence renewal dates are not correctly updated resulting in the licences due data to be incorrect and customer licence renewals are not processed. The customer will then be driving a vehicle that is unroadworthy and in the event of an accident then the insurance company may not honour the insurance claim. The customer could also receive fines for not displaying a valid licence disc. This will all impact on our service delivery and reputation. Desired Outcome Currently the file is uploaded on a monthly basis. With automation this can be done on a weekly basis. This will ensure that all data relating to the assets are correct. Business would prefer an API between Miles and Certrack which through automation requires data within Miles to be validated and updated from the Certrack data/file information. Attached is the SOP that was done relating to the certrack file. It gives an in depth explanation of how the process works. |  | Nicolene Potgieter | Sales - Remarketing | Sandy/ Nkosinathi
32 |  |  | FML-5447 | FML-5475 | BAU | Passed QA | Not Required | Ready for Prod | Lookup table audit |  |  | Nkosinathi Mahlangu | N/A | Sandy/ Nkosinathi