## Slide 1: Retail & Commercial
FML
WesBank IT Area Report
May 2023

## Slide 2: Risk & Audit
Audit/Risk | Due Date | RAG
GIA-577740 SDI - Incomplete vehicle history migrated on Miles | 31 Jan 2023 | Closed – Risk Verified and Approved
GIA-577741 SDI - Incomplete vehicle statuses on Miles | 31 August 2023 | Open
GIA-577743 SDI - Miles inability to pay for supplier work done prior to termination of contract - struggling to find a solution in Miles, Neusa suggests that it be moved to Finance, it was picked up based on customer complaints | 31 Jan 2023 | Closed – Risk Verified and Approved
GIA-577748 SDI - System “auto filling” details of supplier last paid | 31 August 2023 | Open
GIA-577746 SDI - Operating Lease (OPL) Contracts are accessible on Miles for maintenance authorisation - only manual work around that can be achieved, no system solution. Risk acceptance may be needed | 31 Jan 2023 | Closed – Not Risk Verified and Approved
GIA-577876 SDI - System failure in supplier payment processing | 31 July 2023 | Open

## Slide 3: Staff Training, Declarations, etc
Item | Due Date | % Completion
Miles Configuration Training – 10 Miles support resources from both FML Business and IT are attending the training sessions Modules Data Model Foundations Formulas Prod & Pricing | 10 March 2023 | 100%
Miles Configuration Training | TBC – Aug 2023 | 0%
Miles End User Training (M3) – Service Management Team | TBC | 0%

## Slide 4: Upcoming Delivery
Item | Due Date | Concerns
Miles DR Test | 18 June 2023 | The DR Test needs to be conducted before the M3 go live in June. Possible dates are 04 June or 18 June 2023.
M3 Implementation (RT46/SAPS) | 12 June 2023 | Integration with Autocard has still outstanding defects and impacting testing
Miles Web Implementation | TBC | M3 Miles Web is connected to Everest RIA. A ticket has been logged for this change.
M3 Implementation (Corporate) | TBC | 
FleetActiv Decommission | TBC | 
FleetActiv Migration to Windows 2019 | August 2023 | FleetActiv critical resource is also allocated to M3 DM stream. Due dates for both projects cannot be moved.
Scored indicator from CRO to Miles | May 2023 | Clashes with M3 go live
Miles to read SIC codes and FR from Credit Online | May 2023 | Clashes with M3 go live
Migrate company 12 off FleetActiv and investigate VAT treatment for this book | TBC | 
Incorrect settlement calculation for accounts that are in arrears | June 2023 | 
FML Automated Transaction Screening | Aug 2023 | 
New Fines Capability - Platform Solution | March 2024 | 
FML Customer and Merchant Portal | TBC | 

## Slide 5: Delivery in Last Month
Item | Additional Comments
Implementation of Certrack - Bulk licence renewal changes | Implemented on 26 May 2023
Implementation of Shoprite Commercial Restructures | Implemented on 26 May 2023
Successful Shoprite billing post restructures | Executed on 30 May 2023
Successful Billing for May 2023 | Executed on 22 May 2023
Successful Month-End Run May 2023 | Executed on 31 May 2023

## Slide 6: Production Defect/Reschedule Root Cause Analysis
Item | Date | Defect/Reschedule | Root Cause
May Billing Rescheduled | 19/05/2023 | Reschedule | Shoprite billing items needed to be excluded in order to first implementing the restructure fix.
Miles application shutdown | 26/05/2023 | Defect | The server cluster automatically shutdown, due to a host CPU reaching 100%
Miles application shutdown | 31/05/2023 | Defect | Miles lost connection and users could not connect to the application.
May Month-end jobs put on-hold | 31/05/2023 | Defect | Finance requested month-end jobs to be put on hold, in order to validate Shoprite data.

## Slide 7: Miles Month on Month Incident Analysis
Chart: 
| i&SS Service Desk | WesBank Access Management | WesBank Application Support | WesBank Miles Config Team | WesBank Access Management | WesBank Application Support | WesBank Miles Config Team | WesBank Access Management | WesBank Application Support | WesBank Miles Config Team | WesBank Access Management | WesBank Application Support | WesBank Miles Config Team | WesBank MS SQL DBA | WesBank Access Management | WesBank Application Support | WesBank Miles Config Team | WesBank MS SQL DBA | WesBank Globalscape Support | WesBank Wintel Server | Jan | Feb | Mar | Apr | May
Sum of Opened | 1 | 46 | 18 | 25 | 31 | 18 | 30 | 24 | 36 | 29 | 41 | 41 | 24 | 2 | 30 | 46 | 28 | 0 | 1 | 1
Sum of Closed | 1 | 45 | 30 | 11 | 30 | 20 | 29 | 25 | 24 | 22 | 38 | 41 | 36 | 2 | 29 | 49 | 14 | 0 | 1 | 1