## Sheet1
No. | Ativity | Category | Due Date | Status | Comments | Individual taking over activity
1 | Delegation and assignment of FML production issues/incidents to the config team | PROD/EVEREST |  | Ongoing |  | Leeto Modutoane,Mandla Mtombeni
2 | Delegation and assignment of change requests/enhancements | PROD/EVEREST |  | Ongoing |  | Leeto Modutoane,Mandla Mtombeni
3 | Maintenance of the Miles Incident and Requests tracking sheet | PROD/EVEREST |  | Ongoing |  | Nevashin Govindasamy
4 | Miles PRODUCTION patching (two weekly patches) | PROD/EVEREST |  | Ongoing |  | Sekhonyana Molapo,Sibusiso Ndaba
5 | Miles Everest NON-PROD patching (DEV, QA, UAT, PERF) |  |  |  |  | Sekhonyana Molapo,Sibusiso Ndaba
6 | Miles M3 NON-PROD patching (DEV, QA, UAT, PERF) | PROD/EVEREST |  | Ongoing |  | Sekhonyana Molapo,Sibusiso Ndaba
7 | Change and Release Planning and Management of FML deployments to PROD | PROD/EVEREST |  | Ongoing |  | Leeto Modutoane,Mandla Mtombeni
8 | Logging, Monitoring and Deployment of SOFICO Service Desk tickets | PROD/EVEREST |  | Ongoing |  | FML Dev and Config Team
9 | Deployment of the 2022.2 upgrade to PROD, inludes M3 functionality | 2022.2 Upgrade | 2023-01-15 |  | Deployment of the 2022.2 release/upgrade to production. | Leeto Modutoane,Sibusiso Ndaba,Nkosinathi Mahlangu
10 | Control-M configuration on M3 DEV, QA, UAT and PERF | M3 | 30 -Jan-23 |  |  | Nkosinathi Mahlangu
11 | SIT/QA support | M3 |  | Ongoing |  | Nkosinathi Mahlangu,Sibusiso Ndaba
12 | UAT Support | M3 |  | Ongoing |  | Nkosinathi Mahlangu,Sibusiso Ndaba
13 | Maintenance of the Miles Everest deployment tracking sheet | M3/EVEREST |  | Ongoing |  | Sibusiso Ndaba
14 | Team Management (Performance, timesheets,leave,other) | PEOPLE |  | Ongoing |  | Sisanda Meyer
15 | Recruitment of a DEV stage II Developer | PEOPLE | 2023-02-28 |  |  | Sisanda Meyer,Leeto Modutoane
16 | Assist with Tech lead Replacement | PEOPLE |  |  |  | Sisanda Meyer,Candice Govender
17 | Config and Dev stand-ups | PROD/EVEREST |  | Ongoing |  | Leeto Modutoane,Mandla Mtombeni
18 | IT Daily Stand-up,ECAB and CAB attendance | PROD/EVEREST |  | Ongoing |  | Leeto Modutoane
19 | Miles Staging database for reporting | PROD/EVEREST |  |  |  | Themba Sivate
20 | FleetActiv Maintenance | PROD/EVEREST |  |  |  | Ian Wegerle/Mandla Mtombeni/Themba Sivate
21 | FleetActiv Decommission (TFS, INT FINANCE) | PROD/EVEREST |  |  |  | Ian Wegerle,Sisanda Meyer
22 | Monthly CIO report | REPORTING |  |  |  | Leeto Modutoane,Nevashin Govindasamy
23 | SharePoint Reports |  |  |  |  | FML Dev and Config Team
24 | SOFICO xml deployment | PROD/EVEREST |  | Ongoing |  | Mandla Mtombeni
25 | FML IT Daily Stand-Up | PROD/EVEREST |  | Ongoing |  | Mandla Mtombeni
26 | Requirements Session | PROD/EVEREST |  | Ongoing |  | Mandla Mtombeni,Nevashin Govindasamy
27 | Creating BAU Sprint | PROD/EVEREST |  | Ongoing |  | Mandla Mtombeni
28 | SOFICO Mitigation Dashboard | REPORTING |  | Ongoing |  | Mandla Mtombeni,Nevashin Govindasamy,Candice Govender
29 | FML IT Leadership Stand-up |  |  | Ongoing |  | Mandla Mtombeni,Nevashin Govindasamy,Candice Govender